## User Stories
ID | Feature | Sub-feature | Role | User Story | Expected Behavior (from code) | Key Files | Code Status (P1) | Evidence (P1) | Test Result (P2) | Errors / Notes (P2) | Severity (P2) | Fix Applied (P3) | Retest Result (P4)
AUTH-01 | Authentication | Email/password sign-up | Guest | As a guest, I want to register with email, password and a role (student/professor), so that I can access the platform. | signUp calls supabase.auth.signUp with emailRedirectTo=origin/ and data.role; role is set server-side by the on_auth_user_created trigger (NOT client-side); on success student→/onboarding, professor→/dashboard; 'already registered' mapped to localized message. | src/lib/auth.tsx:220; src/pages/Auth.tsx:112 | Functioning | Server-side role via trigger; client upsert explicitly avoided
AUTH-02 | Authentication | Sign-up validation | Guest | As a guest, I want my email/password validated before submit, so that I get immediate feedback. | Zod schema: valid email + password min length 6; field-level errors rendered; submit blocked unless privacy consent checked. | src/pages/Auth.tsx:34,64 | Functioning | Zod + consent gate
AUTH-03 | Authentication | Privacy consent at sign-up | Guest | As a guest, I want to consent to the privacy policy before registering, so that signup is GDPR-compliant. | Checkbox privacyConsent gates submit (disabled when unchecked) and handleSubmit early-returns with destructive toast; links to /datenschutz. | src/pages/Auth.tsx:64,318 | Functioning | Consent enforced in handler + disabled state
AUTH-04 | Authentication | Email/password sign-in | Guest | As a guest, I want to log in with email and password, so that I reach my dashboard. | signInWithPassword; verifies a profiles row exists else signs out with 'account deleted' error; 'Invalid login credentials' localized; logs a login event; redirect deferred to PublicRoute by role. | src/lib/auth.tsx:247; src/pages/Auth.tsx:75 | Functioning | Profile-existence guard + role redirect via guard
AUTH-05 | Authentication | Forgot/reset password | Guest | As a guest, I want to request a password reset email, so that I can recover access. | handleForgotPassword requires email, calls resetPasswordForEmail with redirectTo=origin/reset-password; success/failure toasts. | src/pages/Auth.tsx:145 | Broken | redirectTo /reset-password has NO registered route — user lands on protected 404; reset cannot complete in-app | BROKEN (confirmed) | Password-reset email redirects to /reset-password which had NO route → user landed on protected 404; reset impossible in-app. | High | Added src/pages/ResetPassword.tsx (handles Supabase recovery session via onAuthStateChange+getSession, updateUser({password}), signs out, →/auth; invalid/expired-link + done states). Registered BARE route /reset-password in App.tsx (not PublicRoute, which would bounce the recovery session). Added PublicRoutes.RESET_PASSWORD. | PASS (tsc 0 errors; route resolves). Full recovery-link flow needs live Supabase email.
AUTH-06 | Authentication | Show/hide password | Any | As a user, I want to toggle password visibility, so that I can verify what I typed. | Eye/EyeOff toggles input type; aria-label localized. | src/pages/Auth.tsx:299 | Functioning | Toggle wired
AUTH-07 | Authentication | Toggle sign-in/sign-up | Guest | As a guest, I want to switch between login and registration on one screen. | Button flips isLogin, clears errors; role selector + consent only in signup. | src/pages/Auth.tsx:352 | Functioning | State toggle clears errors
AUTH-08 | Authentication | Sign-out | Any | As a logged-in user, I want to log out, so that my session ends securely. | signOut POSTs /api/auth/logout (Bearer) to invalidate backend token cache (non-blocking), then supabase.auth.signOut() and clears local state. | src/lib/auth.tsx:272; backend/api/v1/auth.py:29 | Functioning | Backend cache invalidation before local wipe
AUTH-09 | Session/token | Session bootstrap & two-phase loading | Any | As a user, I want session+role resolved before routing, so that I avoid flashes/lockups. | onAuthStateChange sets session; defers profile+role fetch in setTimeout(0) once per session (hasFetchedProfile ref) to dodge SDK deadlock; loading = sessionLoading¦¦roleLoading. | src/lib/auth.tsx:111 | Functioning | Race-safety guard + single-fetch ref
AUTH-10 | Session/token | Profile fetch timeout/error UX | Any | As a user, I want a clear signal if my profile fails to load. | fetchProfile returns 'missing'(→signOut) ¦ 'error'(→destructive toast, session kept) ¦ 'ok'; wrapped in withTimeout. | src/lib/auth.tsx:58,140 | Functioning | Explicit missing-vs-error handling
AUTH-11 | Session/token | Missing-profile auto sign-out | Any | As a user whose account row was deleted, I want to be signed out cleanly. | 'missing' result logs warning and calls signOut(). | src/lib/auth.tsx:144 | Functioning | Sign-out on missing profile
AUTH-12 | Session/token | Realtime profile sync | Any | As a user, I want XP/level/streak/language to update live. | Subscribes to postgres_changes UPDATE on profiles filtered by user_id; updates state on payload. | src/lib/auth.tsx:194 | Functioning | Realtime channel per user
AUTH-13 | Session/token | Auth header injection | Any | As a logged-in user, I want API calls to carry my token. | apiClient dedupes concurrent getSession, throws 'Unauthenticated' if none, attaches Bearer, rewrites /api/→/api/v1/, non-2xx throws, 204 returns undefined. | src/lib/apiClient.ts:12 | Functioning | Concurrency guard + path rewrite | PASS | tsc --noEmit: 0 errors. Verified empirically: backend serves only /api/v1/*, but main.py:150 redirect_legacy_api 307-redirects /api/*→/api/v1/* and fetch follows it preserving method+body, so apiClient (rewrites) AND raw fetch() call sites both resolve. NOT a routing bug. | —
AUTH-14 | Access control | Protected route guard (frontend) | Any | As a user, I want unauthenticated access blocked. | ProtectedRoute: spinner while loading; no user→/auth; role not in allowedRoles→/dashboard; unknown role (timeout)→/dashboard. | src/lib/routeGuards.tsx:25 | Functioning | Handles unknown-role timeout case
AUTH-15 | Access control | Public route role redirect | Guest | As a logged-in user, I want bouncing off public pages to my dashboard. | App.tsx inline PublicRoute redirects professor→/professor/dashboard, admin→/admin/dashboard, else→/dashboard. | src/App.tsx:125; src/lib/routeGuards.tsx:57 | Partial | Two divergent PublicRoute impls; routeGuards.tsx version omits admin and appears to be dead duplicate code | Partial (confirmed) | Two divergent guard impls: src/lib/routeGuards.tsx (PublicRoute omits admin redirect) was dead — App.tsx uses its own inline, more-complete guards. Hazard: importing the wrong one. | Low | Deleted unused src/lib/routeGuards.tsx + its test (only covered the dead version). App.tsx inline guards remain the single source. | PASS (tsc 0; vitest 209 = 219-10 deleted-dead-code tests).
AUTH-16 | Access control | Student-only routes | Student | As a student, I want student areas restricted to students. | Routes wrapped ProtectedRoute allowedRoles=['student']; non-students→/dashboard. | src/App.tsx:219 | Functioning | allowedRoles enforced
AUTH-17 | Access control | Professor-only routes | Professor | As a professor, I want my console restricted to professors. | Professor routes wrapped allowedRoles=['professor']. | src/App.tsx:297 | Functioning | allowedRoles enforced
AUTH-18 | Access control | Admin-only routes | Admin | As an admin, I want the admin dashboard restricted to admins. | /admin/dashboard wrapped allowedRoles=['admin']. | src/App.tsx:411 | Functioning | allowedRoles=admin
AUTH-19 | Access control | Dashboard role dispatch | Any | As a user, I want /dashboard to route me appropriately. | StudentDashboardRoute: professor→/professor/dashboard else StudentDashboard; /dashboard route open to any authed user. | src/App.tsx:150 | Functioning | Role dispatch within shared route
AUTH-20 | Access control | Backend token verification | Any | As the system, I want every protected API to validate the JWT. | verify_token: 401 if no creds; blocklist check; 45s L2 cache; else GET Supabase /user (401 on non-200), build CachedUser, cache it; generic exception→401. | backend/core/auth_middleware.py:46 | Functioning | Blocklist + cache + live verify with 401 paths | PASS | test_auth_middleware verify_token (httpx GET /user + cache) green after test reconciliation. | —
AUTH-21 | Access control | Backend role enforcement | Professor/Admin | As the system, I want role-restricted endpoints enforced server-side. | require_role: 401 if no uid; trusts JWT app_metadata.role (server-controlled), falls back to user_roles DB lookup; 403 if no match. | backend/core/auth_middleware.py:159 | Functioning | Uses app_metadata not user_metadata; RLS-locked fallback
AUTH-22 | Access control | Admin token-cache cleanup endpoint | Admin | As an admin, I want to purge expired token-cache rows. | POST /auth/cleanup-token-cache guarded require_role('admin'), 5/min, calls purge_expired_backend_cache. | backend/api/v1/auth.py:57 | Functioning | Admin-gated + rate-limited (was role-less before)
AUTH-23 | Settings | Edit profile name/display name | Any | As a user, I want to set my full/display name. | ProfileForm updates profiles.full_name/display_name (trimmed→null); maxLen 100/50; dirty-tracking; save disabled when unchanged; toasts; triggers gamification.evaluate(). | src/pages/Settings.tsx:260 | Functioning | Dirty-tracking + validation
AUTH-24 | Settings | Email read-only | Any | As a user, I want my email shown but locked. | Email Input readOnly disabled showing profile.email. | src/pages/Settings.tsx:365 | Functioning | Intentionally non-editable
AUTH-25 | Settings | Avatar upload | Any | As a user, I want to upload a profile photo. | Uploads to avatars/<userId>/<ts>.<ext>, sets profiles.avatar_url, refreshes profile, evaluates gamification; broken-image onError falls back to dicebear. | src/pages/Settings.tsx:92 | Functioning | Full upload→persist→refresh
AUTH-26 | Settings | Preset avatar selection | Any | As a user, I want to pick a preset avatar. | handleSelectPreset sets avatar_url to a dicebear preset; 6 presets; toasts. | src/pages/Settings.tsx:137 | Functioning | Preset persistence
AUTH-27 | Settings | Change password | Any | As a user, I want to change my password securely. | Requires current+new(≥6)+matching confirm; re-auths via signInWithPassword (wrong current→toast) then updateUser({password}); clears fields; button disabled until valid. | src/pages/Settings.tsx:429 | Functioning | Current-password re-verification
AUTH-28 | Settings | Export account data (GDPR) | Any | As a user, I want to download my data. | Parallel-queries profiles, student_progress, achievements, learning_events; downloads learnstation-data-YYYY-MM-DD.json. | src/pages/Settings.tsx:611 | Functioning | Client-side export of 4 tables
AUTH-29 | Settings | Delete account / data (GDPR) | Any | As a user, I want to delete my account. | Confirm step; sequentially deletes learning_events, student_progress, achievements, user_roles, profiles (profiles error fatal); signs out and →/. | src/pages/Settings.tsx:649 | Partial | Deletes DB rows client-side but NOT the Supabase auth user — auth identity persists; relies on client cascade ordering
AUTH-30 | Settings | Language preference | Any | As a user, I want EN/DE UI. | setLanguage changes i18n + localStorage, and when signed-in persists profiles.preferred_language (non-fatal on failure); resolution profile→localStorage→browser. | src/pages/Settings.tsx:736 | Functioning | Persisted + graceful fallback
AUTH-31 | Settings | AI model preference | Any | As a user, I want to pick an AI provider. | Grid of 4 models (cerebras/groq/openrouter/cloudflare); save appears on change; setAiModel via useAiModel; toast. | src/pages/Settings.tsx:782 | Functioning | Pending-vs-saved diff
AUTH-32 | Settings | Institution email verification | Any | As a user, I want to link my university email to unlock institution features. | Settings renders <UniversityEmailLink/> under 'Institution verification'. | src/pages/Settings.tsx:383 | Unclear | Behavior in UniversityEmailLink (see ONB-07); only placement confirmed here
AUTH-33 | Settings | Academic profile editor | Any | As a user, I want to set university/program/courses for recommendations. | Settings renders <AcademicProfileEditor/> under 'Academic profile'. | src/pages/Settings.tsx:388 | Unclear | Delegated to AcademicProfileEditor (see ONB-10)
AUTH-34 | Settings | Settings access gating | Any | As any authed user, I want settings reachable. | /settings ProtectedRoute (no allowedRoles → any authed); SettingsWrapper wraps in ConsoleLayout; LoadingSkeleton until profile loaded. | src/App.tsx:289; src/pages/Settings.tsx:879 | Partial | SettingsWrapper role branch returns identical JSX both arms — dead branching | Partial (confirmed) | SettingsWrapper had a role branch whose two arms returned identical JSX (dead branching). | Low | Collapsed to a single ConsoleLayout<Settings/> return. | PASS (tsc 0).
AUTH-35 | Legal/public | Impressum page | Guest | As any visitor, I want the legal imprint (German law). | Public route; localized imprint sections, language toggle, back-home link. | src/App.tsx:205; src/pages/Impressum.tsx:6 | Functioning | Public i18n static content
AUTH-36 | Legal/public | Datenschutz (privacy) page | Guest | As any visitor, I want the privacy policy. | Public route; 8 localized sections via i18n returnObjects + Trans; contact email; back-home link. | src/App.tsx:206; src/pages/Datenschutz.tsx:20 | Functioning | Public i18n
AUTH-37 | Legal/public | Landing page & auth entry | Guest | As a visitor, I want a landing page with sign-in CTAs. | / is PublicRoute (redirects authed users by role); buttons navigate to /auth. | src/App.tsx:203; src/pages/Landing.tsx:311 | Functioning | CTAs wired to /auth
AUTH-38 | Access control | Authenticated 404 handling | Any | As a user hitting an unknown URL, I want a sensible 404. | ProtectedNotFound: no user→bare NotFound; else NotFound inside ConsoleLayout. | src/App.tsx:176 | Partial | professor/non-professor branches identical JSX — redundant | Partial (confirmed) | ProtectedNotFound professor/non-professor branches returned identical JSX. | Low | Collapsed to authed→shell / unauthed→bare NotFound. | PASS (tsc 0).
AUTH-39 | Authentication | Generic/network error handling | Guest | As a guest, I want auth failures surfaced. | handleSubmit try/catch shows generic destructive toast on unexpected throw; loading reset in finally. | src/pages/Auth.tsx:134 | Functioning | Catch-all + finally reset
PDF-01 | PDF pipeline | Upload PDF + parse to slides (streaming) | Professor | As a professor, I upload a PDF and watch it parse into slides with titles, content, summaries and a deck quiz. | POST /api/upload/parse-pdf-stream validates (≤25MB, ≤300 pages, PDF magic), sha256, cache check, streams SSE (info/phase/meta/progress/slide/deck_complete/complete). Live path PARSER_VERSION=5 → unified_orchestrator (server-authoritative: creates lecture + persists slides/quizzes/embeddings). | backend/api/v1/upload.py:48; backend/services/upload_service.py:128; backend/services/parser/unified_orchestrator.py:152 | Functioning | v5 unified live via .env PARSER_VERSION=5 | PASS | test_unified_orchestrator suite green (happy path, replay, resume, missing-pdf). | —
PDF-02 | PDF pipeline | Parser version selection | Admin | As an operator, the active pipeline is chosen by PARSER_VERSION (2/3/4/5). | process_pdf_stream branches on settings.parser_version: 5 unified, 4/v4 Arq, 3 v3 Arq, else legacy parse_pdf_stream. | backend/services/upload_service.py:162; backend/core/config.py:46 | Partial | .env=5 live but .env.example + config default still 2 — docs/default drift | Partial (confirmed) | .env=5 (live) but config default + .env.example said 2 → fresh deploy w/o env var silently ran old v2 pipeline. | Medium | Set config.py parser_version default '2'→'5' and .env.example PARSER_VERSION 2→5 to match live. | PASS (backend 638 green with default=5).
PDF-03 | PDF pipeline | Configurable LLM for unified parse | Admin | As an institution, the unified synthesis model is server-configured, not per-upload. | unified_ai_model = _cfg.parser_llm_model or ai_model (default cerebras); vision uses settings.vision_model (default gemini-2.0-flash). | backend/services/upload_service.py:180; backend/core/config.py:50 | Functioning | Server-authoritative model
PDF-04 | PDF pipeline | 'Skip AI' / on_demand parsing mode | Professor | As a professor, I pick 'Skip AI' so import only extracts text and I enhance per-slide later. | Frontend sends parsing_mode=on_demand; usePDFUpload forwards it. BUT the unified (v5) branch never reads parsing_mode — always runs full AI synth + quiz. Honored only on legacy path. | src/pages/LectureUpload.tsx:779; backend/services/upload_service.py:168 | Broken | on_demand toggle is a no-op under live v5 | BROKEN (confirmed) | 'Skip AI'/on_demand toggle is a no-op under live v5 (unified branch never reads parsing_mode; always full-AI synth). | Medium | DEFERRED — needs product decision: (a) honor on_demand in the unified pipeline (skip synthesis) = real pipeline work, or (b) hide the toggle when v5 is live (frontend can't currently see PARSER_VERSION). Not silently changed.
PDF-05 | PDF pipeline | use_blueprint option | Professor | As a tester, I enable 'Use Blueprint' on the pipeline lab. | use_blueprint only threaded into legacy parse_pdf_stream; unified/v4/v3 ignore it. | backend/services/upload_service.py:362; src/pages/PipelineTestPage.tsx:410 | Partial | Dead option under v4/v5 | Partial (confirmed) | use_blueprint only threaded into the legacy parser; ignored by v4/v5. | Low | DEFERRED — dev/Pipeline-Lab-only option; harmless no-op. Left as-is (documenting rather than removing a tester control).
PDF-06 | PDF pipeline | Streaming progress UX (overlay) | Professor | As a professor, I see extract→enhance→finalize phases + per-slide progress, and the overlay auto-dismisses on completion. | PDFUploadOverlay driven by usePDFUpload SSE; parseCompleted set only on complete event → 800ms auto-close; error/cancel keep overlay open. | src/hooks/usePDFUpload.ts:140; src/components/PDFUploadOverlay.tsx | Functioning | complete-gated stepper
PDF-07 | PDF pipeline | Upload timeout / abort | Professor | As a professor, a stuck upload aborts after 10 min and I can cancel manually. | 10-min AbortController; closeUploadOverlay aborts; AbortError swallowed (no toast). | src/hooks/usePDFUpload.ts:115 | Functioning | 10-min cap
PDF-08 | PDF pipeline | Duplicate PDF detection | Professor | As a professor, re-uploading a PDF I already made a lecture from prompts me to open the existing lecture or upload as new. | sha256 → /check-duplicate (scoped to user_id) → DuplicatePDFDialog; 'Use existing' navigates, 'Upload as new' forceReparse. | src/hooks/usePDFUpload.ts:296; backend/api/v1/upload.py:229 | Functioning | Per-professor scoped | PASS | test_check_duplicate green; /api/upload/check-duplicate resolves via 307 compat redirect. | —
PDF-09 | PDF pipeline | Parse-cache hit prompt | Professor | As a professor, if the same PDF was parsed before (no lecture), I'm asked to use the cached parse or re-parse. | /check-parse-cache (global pdf_parse_cache) → ParseCacheDialog; 'Use saved' replays cached SSE; 'Re-parse' forces fresh. | src/hooks/usePDFUpload.ts:334; backend/api/v1/upload.py:252 | Functioning | Distinct from duplicate check
PDF-10 | PDF pipeline | Cached parse replay / invalidation | Professor | As a professor, a cache hit replays slides without re-running the LLM. | cached_stream replays slides+deck; parser-match guard invalidates only when requested resolves to v4/v3; at PARSER_VERSION=5 requested='auto' and never invalidates a v4 cache. | backend/api/v1/upload.py:89 | Partial | v5 not in cache-invalidation guard → v4 cache served under v5
PDF-11 | PDF pipeline | Idempotent re-parse (unified) | Professor | As a professor, re-enqueuing a completed parse replays from DB instead of duplicating the lecture. | parse_pdf_unified dedupes on (pdf_hash,'5'); COMPLETED→_replay_from_db; partial reuses lecture and rewrites slides. | backend/services/parser/unified_orchestrator.py:190 | Functioning | Run-level idempotency
PDF-12 | PDF pipeline | Per-slide synthesis (text vs vision) | Professor | As a professor, each slide gets a real title + professor-voice explanation; image-only slides go through vision OCR. | _synthesize_slide: ≥25 chars→analyze_slide (text LLM); else render JPEG + analyze_slide_vision; never raises, falls back to raw text. | backend/services/parser/unified_orchestrator.py:88 | Functioning | 25-char threshold routes vision
PDF-13 | PDF pipeline | Vision provider fallback chain | Admin | As an operator, vision tries the preferred provider then falls back across groq/gemini/openai. | _sync_analyze_vision builds provider list, reorders by ai_model, tries each, returns _FALLBACK_RESULT if all fail. | backend/services/ai/vision.py:91 | Functioning | Graceful degrade to fallback dict
PDF-14 | PDF pipeline | Deck-level quiz + answer correctness | Professor | As a professor, the lecture gets a cross-slide quiz whose answer key is correct. | _map_deck_quiz resolves correctAnswer via _normalize_answer_index (text/letter/index); unresolvable questions DROPPED not defaulted to A; slideId(1-based)→0-based linked_slides. | backend/services/parser/v4_orchestrator.py:107 | Functioning | Drops bad answers vs silent wrong key | PASS | test_v4_quiz_mapping green (answer normalization, bad-answer drop). | —
PDF-15 | PDF pipeline | Per-slide quizzes under unified | Professor | As a professor, I expect each slide to carry its own quiz after parsing. | Unified emits each slide with questions:[] and never calls persist.insert_slide_quizzes — only a deck-level quiz is generated/persisted. | backend/services/parser/unified_orchestrator.py:271; backend/services/parser/persist.py:148 | Partial | No per-slide quiz from v5 parse
PDF-16 | PDF pipeline | Auto-generated client quiz suggestions | Professor | As a professor, after import the app auto-suggests quizzes per slide. | LectureUpload auto-runs handleGenerateAllQuizzes on completion; but when v5 sets serverLectureId, save path only PATCHes metadata and never persists these suggestions. | src/pages/LectureUpload.tsx:499; src/hooks/useLectureSubmit.ts:65 | Partial | Suggestions lost on v5 save path
PDF-17 | PDF pipeline | Embeddings for tutor (RAG) | Professor | As a professor, parsed slides are embedded so the AI tutor can answer about them. | _safe_embedding_task per slide (keyed by pdf_hash); finalize attaches embeddings to lecture; non-metadata slides only. | backend/services/parser/unified_orchestrator.py:245; backend/api/v1/upload.py:114 | Functioning | Fire-and-forget embeddings
PDF-18 | PDF pipeline | Error / partial-failure UX | Professor | As a professor, a parse failure shows a readable error and partial slides aren't silently lost. | Legacy emits partial_complete+error{recoverable}; unified emits error and finalizes lecture with persisted slides; frontend throws on error→toast; overlay stays open. | backend/services/upload_service.py:371; src/hooks/usePDFUpload.ts:270 | Functioning | Partial slides persisted in v5
PDF-19 | Lecture edit | Save lecture (server-authoritative) | Professor | As a professor, I click Save after a v5 parse and my title/description/course are applied. | serverLectureId set → useLectureSubmit only UPDATEs lectures row + triggers concept ingestion (slides/quizzes already persisted). Legacy path inserts everything client-side. | src/hooks/useLectureSubmit.ts:43 | Functioning | Two distinct save paths
PDF-20 | Lecture edit | Edit a parsed lecture | Professor | As a professor, I open a lecture, edit slide title/content/summary/quizzes and save. | LectureEdit fetches slides+quiz_questions, edits in place, saves via update + updateQuizQuestion/insertQuizQuestion; can delete slides; resolves signed PDF URL. | src/pages/LectureEdit.tsx:64 | Functioning | Full CRUD on slides/quizzes
PDF-21 | Lecture edit | On-demand AI generation in editor | Professor | As a professor, I generate title/summary/content/quiz per slide and a deck quiz in the editor. | Calls /api/ai/generate-summary, /suggest-title, /suggest-content, /generate-quiz, /api/ai/decks/{id}/generate-quiz; deck quiz needs ≥2 slides; ai_model from useAiModel. | src/pages/LectureEdit.tsx:325; backend/api/v1/slides_ai.py:212 | Functioning | Per-slide + deck regen
PDF-22 | Fast upload | Isolated fast-upload pipeline | Professor | As a professor, I drop a PDF on Fast Upload and poll until the lecture is built end-to-end. | POST /api/fast-upload/ stores PDF, inserts parse_runs(processing), spawns background process_upload_isolated (pymupdf→per-slide+meta+quiz via LLM→atomic DB writes), returns run_id; frontend polls /status/{run_id} every 3s. | backend/api/v1/fast_upload.py:154; src/pages/FastUpload.tsx:45 | Functioning | Separate from main pipeline
PDF-23 | Fast upload | Fast-upload hardcoded model | Admin | As an institution, fast-upload should use the configured LLM. | analyze_slide_fast/analyze_lecture_meta_fast/generate_quiz_questions_fast hardcode model='gemini/gemini-2.0-flash', ignoring PARSER_LLM_MODEL. | backend/api/v1/fast_upload.py:62 | Partial | Hardcoded gemini, not configurable | Partial (confirmed) | Fast-upload hardcoded model='gemini/gemini-2.0-flash' in 3 functions, ignoring the configurable-LLM design. | Low | Added settings.fast_upload_model (FAST_UPLOAD_MODEL, litellm-format, default unchanged = gemini/gemini-2.0-flash) and referenced it in all 3 acompletion calls. | PASS (backend 638; import OK).
PDF-24 | Fast upload | Fast-upload quiz answer correctness | Professor | As a professor, fast-upload quizzes have a correct answer key. | Each quiz row uses _normalize_answer_index; unresolvable dropped (logged); anchored to slideId or first slide; status completed/error. | backend/api/v1/fast_upload.py:241 | Functioning | Drops bad answers (ported in merge)
PDF-25 | Fast upload | Background-task durability | Admin | As an operator, a fast-upload task isn't GC'd mid-flight and crashes are logged. | _BACKGROUND_TASKS strong refs; done-callback logs cancel/exceptions; user_id UUID validated before spawn. | backend/api/v1/fast_upload.py:20 | Functioning | Strong task refs
PDF-26 | Pipeline test | Pipeline Test Lab (SSE inspector) | Professor | As a tester, I run the full pipeline and inspect per-event SSE, per-slide AI output, questions, deck, and rate slides. | PipelineTestPage streams /parse-pdf-stream, renders events/slides/deck tabs, route/layout stats, evaluation export; parser/aiModel/blueprint/forceReparse controls. | src/pages/PipelineTestPage.tsx:300 | Functioning | Dev inspector UI
PDF-27 | Pipeline test | Test-lab expects v4-style metadata | Professor | As a tester, I see route/engine/tokens/layout_features and route counts per slide. | Page reads slide._meta + question.answer (letter). Live v5 emits flat slides with NO _meta and deck quiz uses correctAnswer index → stats show 0, route/layout panels empty, deck correct-option highlight wrong. | src/pages/PipelineTestPage.tsx:64; backend/services/parser/unified_orchestrator.py:271 | Partial | UI built for v4 meta, mismatched under v5 | Partial (confirmed) | Pipeline Test Lab reads slide._meta + question.answer (v4 shape); v5 emits flat slides + correctAnswer index → route/layout/token stats empty, deck correct-option highlight wrong. | Low | DEFERRED — professor-only internal dev inspector, not a student/prof production surface. Tracked for a v5-aware rework.
PDF-28 | Pipeline test | Raw parser-only output | Professor | As a tester, I extract raw text per page without AI. | /api/upload/parse-raw → extract_raw_pages (auto=ODL then pymupdf); per-page text/char/word counts in side sheet. | src/pages/PipelineTestPage.tsx:365; backend/api/v1/upload.py:301 | Functioning | No-AI extraction view
PDF-29 | PDF pipeline | Parser engine selector label drift | Professor | As a professor, I choose an extraction engine (Auto/LlamaParse/MinerU/OpenDataLoader/PyMuPDF). | LectureUpload labels Auto as 'v4 Recommended'. Under v5 all funnel into unified; only odl/mineru/llamaparse pre-extract; label says v4 but runs v5. | src/pages/LectureUpload.tsx:763; backend/services/upload_service.py:146 | Partial | UI label says v4, runs v5 | Partial (confirmed) | Parser selector labeled Auto as 'v4 Recommended' though live pipeline is v5. | Low | Relabeled to 'Auto (Recommended)' (version-agnostic). | PASS (tsc 0).
PDF-30 | PDF pipeline | Lazy import path | Professor | As a professor, I can import a PDF lazily (text now, synth per-slide on demand). | /import-pdf-lazy (process_pdf_lazy) + /lazy-slides/{hash}/{idx} (synthesize_slide) + /lazy-deck-quiz; used when usePDFPipelineMode isLazy. | backend/api/v1/upload.py:148 | Functioning | Alternate lazy mode
PDF-31 | PDF pipeline | Cache cleanup / attach-lecture utilities | Professor | As a professor, stale checkpoints are purgeable and embeddings attach to my saved lecture. | /cleanup-cache purges expired slide checkpoints; /attach-lecture validates ownership+pdf_hash then attaches embeddings + backfills lectures.pdf_hash. | backend/api/v1/upload.py:268 | Functioning | Ownership-checked
PDF-32 | PDF pipeline | Stray debug auth scripts | Admin | (Housekeeping) test_auth.py / test_auth2.py are ad-hoc debug scripts at backend root. | Untracked files calling supabase_admin.auth.get_user with a fake token; not tests, not wired into any suite. | backend/test_auth.py; backend/test_auth2.py | Unclear | Leftover debug scripts — candidate for removal
CRS-01 | Course mgmt | Create course | Professor | As a professor, I create a course with title (required), optional description and color. | POST /api/courses (require_professor) inserts courses row owned by caller; title 1-200; empty desc→null; returns course with lecture_count=0; toast + refresh. | backend/api/v1/courses.py:416; src/pages/ProfessorCourses.tsx:77 | Functioning | Endpoint + dialog wired | PASS | test_courses_endpoints create/list/get green after fake-supabase timestamp fix. | —
CRS-02 | Course mgmt | Edit course | Professor | As a professor, I edit a course's title/description/color. | PATCH /api/courses/{id} verifies ownership (403/404); applies only provided fields (model_fields_set); returns refreshed course. | backend/api/v1/courses.py:453 | Functioning | Ownership-checked update
CRS-03 | Course mgmt | AI-generate course description | Professor | As a professor, I auto-write a description from the course's lectures. | POST /api/ai/course-description (course_id) → generate_course_description (default cerebras); button disabled when lecture_count==0. | src/pages/ProfessorCourses.tsx:101; backend/api/v1/ai_content.py:345 | Functioning | Endpoint + gating
CRS-04 | Course mgmt | Delete course | Professor | As a professor, I delete a course. | UI blocks delete if lecture_count>0; DELETE /api/courses/{id} ownership-checked; 409 if lectures remain unless ?reassign_to=<id>; empty course deleted; confirm() dialog. | backend/api/v1/courses.py:506; src/pages/ProfessorCourses.tsx:120 | Functioning | UI gate + backend 409/reassign
CRS-05 | Course mgmt | Archive course | Professor | As a professor, I archive a course to hide it from active lists. | confirm() then PATCH is_archived=true; archived excluded from default list + /browse. | backend/api/v1/courses.py:190; src/pages/ProfessorCourses.tsx:140 | Functioning | Archive flag flow
CRS-06 | Course mgmt | List own courses | Professor | As a professor, I see my courses as cards with lecture counts. | GET /api/courses (professor) filters professor_id=uid, excludes archived, cursor-paginated; lecture_count batch-counts non-archived lectures. | backend/api/v1/courses.py:163 | Functioning | Role-aware list
CRS-07 | Course detail | View course + its lectures | Professor | As a professor, I open a course to see assigned lectures. | GET /api/courses/{id} returns course + lectures (owner sees all non-archived); detail page renders cards with Edit/Worksheets. | backend/api/v1/courses.py:347; src/pages/ProfessorCourseDetail.tsx:38 | Functioning | Owner sees full roster
CRS-08 | Lecture-course | Assign existing lecture to course | Professor | As a professor, I add an existing unassigned lecture to a course. | POST /api/courses/{cid}/lectures/{lid} verifies prof owns both; sets lectures.course_id; picker lists prof lectures minus assigned. | backend/api/v1/courses.py:571; src/pages/ProfessorCourseDetail.tsx:53 | Functioning | Ownership-checked assign
CRS-09 | Lecture-course | Upload new lecture into course | Professor | As a professor, from course detail I upload a lecture pre-scoped to this course. | Navigates /professor/upload?courseId={id}; LectureUpload reads courseId, pre-selects, passes into useLectureSubmit. | src/pages/ProfessorCourseDetail.tsx:129; src/pages/LectureUpload.tsx:320 | Functioning | courseId prefill
CRS-10 | Lecture-course | Remove lecture from course | Professor | As a professor, I remove a lecture from a course (also archives it). | confirm() warns archive; DELETE /api/courses/{c}/lectures/{l} sets course_id=null then archiveLecture(); toast. | backend/api/v1/courses.py:605; src/pages/ProfessorCourseDetail.tsx:77 | Functioning | Unassign + archive combined
CRS-11 | Archive | View archived courses & lectures | Professor | As a professor, I open Archive, toggle Courses/Lectures, search. | Courses tab listCourses({onlyArchived:true}); Lectures tab fetchProfessorLectures(onlyArchived); client title/desc search. | backend/api/v1/courses.py:190; src/pages/ProfessorArchive.tsx:46 | Functioning | Archived listing + search
CRS-12 | Archive | Restore archived course | Professor | As a professor, I restore an archived course. | updateCourse(is_archived:false); removed from archive list optimistically; toast. | src/pages/ProfessorArchive.tsx:72 | Functioning | Restore via PATCH
CRS-13 | Archive | Permanently delete archived course | Professor | As a professor, I permanently delete an archived course. | Blocked if lecture_count>0; else confirm() then deleteCourse (same 409/empty rules). | src/pages/ProfessorArchive.tsx:93 | Functioning | Guarded purge
CRS-14 | Archive | Restore/purge archived lecture | Professor | As a professor, I restore or permanently delete an archived lecture. | Restore→unarchiveLecture; Purge→confirm() then deleteLecture (warns purges slides/quizzes/progress). | src/pages/ProfessorArchive.tsx:123 | Functioning | Lecture archive ops
CRS-15 | Discovery | Browse course catalog | Student | As a student, I browse all available courses. | GET /api/courses/browse returns ALL non-archived courses (no enrollment filter), professor_id nulled, with lecture_count; enrolled marked 'Enrolled' disabled. | backend/api/v1/courses.py:235; src/features/student/components/CourseCatalogSheet.tsx:167 | Functioning | Open catalog browse
CRS-16 | Discovery | Recommended courses | Student | As a student, I see personalized course recommendations with a reason. | getRecommendedCourses → RPC get_recommended_courses (excludes enrolled); shows reason + lectureCount + Enroll. | src/features/student/components/CourseCatalogSheet.tsx:38 | Functioning | RPC-backed recs
CRS-17 | Enrollment | Enroll in a course | Student | As a student, I enroll in a catalog/recommended course. | POST /api/courses/{id}/enroll (require_student) upserts course_enrollments (idempotent on conflict); invalidates student queries; toast; sheet stays open. | backend/api/v1/courses.py:288; src/features/student/components/CourseCatalogSheet.tsx:46 | Functioning | Idempotent enroll
CRS-18 | Enrollment | Unenroll from a course | Any | As a student, I leave a course. | DELETE /api/courses/{id}/enroll (require_student) deletes enrollment row, 204. No frontend caller exists. | backend/api/v1/courses.py:322 | Partial | Endpoint exists, no UI
CRS-19 | Enrollment | Enrollment-aware visibility (backend) | Student | As a student, backend computes which courses I may see. | _student_visible_course_ids unions course_enrollments + assignment-reachable courses; GET /api/courses + /{id} filter to this set; single-course view limits to assignment-enrolled lectures. | backend/api/v1/courses.py:110 | Functioning | Two-path visibility | PASS | test_courses_endpoints student-sees-only-enrolled green. | —
CRS-20 | Student library | Browse course library (console UI) | Student | As a student, I open /library and navigate courses/lectures console-style. | StudentCourseLibrary groups data.lectures by course_id into rails, keyboard/controller nav, semester grouping, inline player; empty state offers catalog. | src/pages/StudentCourseLibrary.tsx:91 | Functioning | Library renders/navigates
CRS-21 | Student library | Library data bypasses enrollment filter | Student | As a student, my library shows my courses/lectures. | useStudentDashboard loads via fetchStudentCourses (all, limit 100) + fetchStudentLectures (all non-archived, limit 200) DIRECT from Supabase — NOT the enrollment-aware /api/courses. Visibility governed by RLS, not course_enrollments. | src/features/student/hooks/useStudentDashboard.ts:54; src/services/studentService.ts:18 | Unclear | Client reads tables directly; 'Enrolled' badge may not reflect course_enrollments
CRS-22 | Student course view | View single course (legacy timeline) | Student | As a student, I navigate /course/:id and see lectures as a vertical timeline. | StudentCourseView filters data.lectures by course_id, sorts by title badge then created_at, highlights first uncompleted as 'Next up'; lecture click→/lecture/:id; 'Try new view'→/course-v3/:id. | src/pages/StudentCourseView.tsx:10 | Functioning | Legacy timeline view
CRS-23 | Student course view | Course details sheet | Student | As a student, I view course details (outcomes, rating, lectures). | CourseDetailsSheet shows title/desc, whatYouWillLearn, averageRating/ratingCount, lecture list; outcomes/rating fall back to hardcoded placeholders when absent. | src/pages/StudentCourseLibrary.tsx:820 | Partial | Ratings/outcomes are hardcoded placeholders (4.8, 124, 'Master the fundamentals') | Partial (confirmed) | Course details sheet showed FABRICATED ratings (4.8 / 124) + generic 'what you'll learn' when real data absent — misleading. | Low | Dropped fake fallbacks (averageRating→undefined, ratingCount→0, outcomes→[]); CourseDetailsSheet only renders the rating block when ratingCount>0 && averageRating!=null. | PASS (tsc 0; vitest 209).
CRS-24 | Lecture open | Open a lecture in course context | Any | As a student, I open a lecture inline or full-page. | openInline renders InlineLecturePlayer with courseTitle; 'Expand'→/lecture/:id; /lecture/:id is ProtectedRoute with NO role restriction. | src/pages/StudentCourseLibrary.tsx:311 | Functioning | Inline + full-page open
CRS-25 | Student library | Remember last opened course | Student | As a student, the library reopens focused on my last-used course. | open/openInline write localStorage ascend_last_opened_course; course sort prioritizes it; deep-link courseId preselects. | src/pages/StudentCourseLibrary.tsx:82 | Functioning | localStorage recency
CRS-26 | Course slug | Open course by slug | Any | As a user, a non-UUID course identifier resolves to the real course. | getCourse detects non-UUID, resolves by matching toSlug(title) against listCourses then browseCourses; throws if no match. | src/services/coursesService.ts:56 | Functioning | Slug→id fallback
CRS-27 | Student library | Hardcoded course ordering | Student | As a student, the library shows courses in a sensible order. | courseList sort hardcodes /database/i.test(title) to rank first, then has-lectures, last-opened, progress. | src/pages/StudentCourseLibrary.tsx:165 | Partial | Demo-specific 'Database Systems first' bias | Partial (confirmed) | Library course sort hardcoded /database/i.test(title) to force 'Database Systems' first — demo bias. | Low | Removed the bias; sort is now has-lectures → last-opened → progress. Updated stale comment. | PASS (tsc 0; vitest 209).
CRS-28 | Course mgmt | Active vs archived lecture counts | Professor | As a professor, course cards show a lecture count. | Active courses count non-archived lectures; archived courses count ALL; delete guard counts ALL regardless of archive. | backend/api/v1/courses.py:218 | Functioning | Count rules differ by context (intentional)
AI-01 | AI tutor | Ask tutor about lecture/slide | Student | As a student viewing a lecture, I ask the AI tutor questions and get grounded answers. | POST /api/v1/ai/chat runs chat_with_lecture: sanitize input, embed question, retrieve top-5 lecture-scoped slides via pgvector match_slides (0.65), Socratic prompt, LLM via failover, returns {reply, citations}. | backend/services/ai/chat_service.py:9; backend/services/ai/tutor.py:128; src/components/LectureChat.tsx:170 | Functioning | Full RAG path wired | BLOCKED→PASS | Backend un-importable: tutor.py:124 IndentationError (orphaned dead code from removed refusal helper) broke main + all tutor-importing routers. Import-checks pass after fix. | Critical | Removed orphaned `return False`/`return True` at tutor.py:123-125.
AI-02 | AI tutor | RAG grounding on lecture context | Student | As a student, I want answers from the actual lecture slides, not generic knowledge. | retrieve_relevant_slides embeds query (gemini-embedding-001, 768-dim), match_slides RPC, filters to lecture_id/pdf_hash, top-K, anchors current slide first. | backend/services/ai/retrieval.py:28; backend/services/ai/embeddings.py:13 | Partial | If GEMINI_API_KEY unset, embeddings return zero vector → retrieval degrades to current-slide-only
AI-03 | AI tutor | Supplementary knowledge in blockquotes | Student | As a student, I want info beyond the slides clearly marked. | Prompt instructs wrapping non-context knowledge in Markdown blockquotes; frontend styles prose-blockquote distinctly. | backend/services/ai/tutor.py:183; src/components/LectureChat.tsx:447 | Functioning | Prompt-instructed (not enforced)
AI-04 | AI tutor | Citation chips & slide jump | Student | As a student, I see which slides an answer came from and jump to them. | _extract_citations parses [Slide N], keeps only retrieved indices (hallucinations dropped); chips call onSlideJump. | backend/services/ai/tutor.py:94; src/components/LectureChat.tsx:455 | Functioning | Hallucinated refs filtered server-side | PASS | _extract_citations compiles+imports clean after tutor.py fix. | —
AI-05 | AI tutor | Prompt-injection hardening | Any | As the system, I want student input not to override tutor instructions. | _sanitize_user_input truncates, strips null bytes, HTML-escapes, rewrites injection phrases to [student-quoted:…]; history sanitized too. | backend/services/ai/tutor.py:34 | Functioning | Neutralize-not-block
AI-06 | AI tutor | Persistent chat sessions | Student | As a student, I want tutor conversations saved and resumable. | /api/v1/ai/sessions (create/list), /sessions/{id}/messages, DELETE; process_chat_request verifies ownership + lecture auth, loads last 20 from chat_memory, appends turns. | backend/api/v1/ai_content.py:239; backend/services/ai/chat_service.py:46 | Functioning | Ownership + lecture-auth checks; LectureChat doesn't pass session_id
AI-07 | AI tutor | Failure / connection handling | Student | As a student, I want a graceful message when the tutor can't respond. | Retrieval failure→slide_text grounding; LLM failure→'having trouble connecting'; other errors→ValueError→HTTP 500; frontend shows chat.connectionError. | backend/services/ai/tutor.py:209; src/components/LectureChat.tsx:265 | Functioning | Multiple fallback layers
AI-08 | AI tutor | Streaming negotiation mismatch | Student | As a student, I expect the tutor reply to appear (streamed or whole). | Frontend sends Accept: text/event-stream and tries streaming first, but backend /ai/chat returns plain JSON; frontend JSON branch handles it. | src/components/LectureChat.tsx:169; backend/api/v1/ai_content.py:195 | Partial | Streaming code path is dead (backend never streams); JSON fallback always taken | Partial (confirmed) | LectureChat sent Accept: text/event-stream and had a full SSE branch, but backend /ai/chat only returns JSON → SSE path was dead. | Low | Removed the dead SSE branch + reader loop; kept the JSON path; Accept→application/json. finally{} still resets streamingRef. | PASS (tsc 0; vitest LectureChat green).
AI-09 | Lecture viewing | View lecture & navigate slides | Student | As a student, I open a lecture and move through its slides. | LectureView fetches lecture/slides/quiz; tracks currentSlideIndex via useSlideProgress; prev/next; logs logSlideView with elapsed. | src/pages/LectureView.tsx:8; src/features/student/components/InlineLecturePlayer.tsx:327 | Functioning | —
AI-10 | Lecture viewing | Per-slide quiz taking | Student | As a student, I answer a quiz tied to a slide and earn XP. | Quiz filtered by slide_id; QuizCard after slide; handleQuizAnswer records, logs quiz_attempt, grants 10 XP on correct, sweeps badges; Continue advances. | src/pages/LectureView.tsx:345 | Functioning | —
AI-11 | Lecture viewing | Cross-slide deck quiz chips | Student | As a student, I want deck-level quiz questions linking multiple slides. | Deck quiz items persisted with metadata.linked_slides; anchored to first linked slide; player renders slide-jump chips. | src/pages/LectureView.tsx:342; backend/api/v1/slides_ai.py:269 | Functioning | Requires ≥2 valid linked slides else dropped
AI-12 | Lecture viewing | Lecture tagline | Student | As a student browsing, I want a one-line AI tagline per lecture. | useLectureTagline POSTs /api/ai/lecture-tagline; generate_lecture_tagline concatenates slide summaries (≤6000), prompts LLM, caches per lecture_id:slide_count. | src/features/student/hooks/useLectureTagline.ts:23; backend/services/ai/tutor_service.py:304 | Functioning | In-process per-worker cache (512 cap)
AI-13 | AI content gen | Per-slide summary generation | Professor | As a professor, I want AI to summarize a slide. | POST /api/ai/generate-summary → generate_summary: metadata-slide filter then generate_deck_summary via QUALITY_CHAIN. | backend/api/v1/ai_content.py:100; backend/services/ai/tutor_service.py:56 | Functioning | generate_summary aliases generate_deck_summary | PASS | test_ai_endpoints TestSummary green (generate_summary via tutor_service). | —
AI-14 | AI content gen | Per-slide quiz generation | Professor | As a professor, I want AI to generate a quiz for a slide. | POST /api/ai/generate-quiz and /slides/{id}/generate-quiz: generate_slide_quiz with validator + 1 regen; normalizes answer→correctAnswer; slides_ai variant persists + flips ai_enhanced. | backend/api/v1/slides_ai.py:212; backend/services/ai/orchestrator.py:1356 | Functioning | — | PASS | test_ai_endpoints TestQuiz green. | —
AI-15 | AI content gen | Slide title/content enhancement | Professor | As a professor, I want AI to suggest a title and rewrite content. | /api/ai/suggest-title, /suggest-content, and slides_ai /regenerate-title & /rewrite-content (persist + flip ai_enhanced + invalidate analytics cache). | backend/api/v1/ai_content.py:124; backend/api/v1/slides_ai.py:152 | Functioning | —
AI-16 | AI content gen | Regenerate slide from PDF (vision) | Professor | As a professor, I want to re-extract a slide from the source PDF via vision. | POST /slides/{id}/regenerate-content → regenerate_slide: ownership check, SSRF-guarded URL validation (HTTPS, no redirects, ≤50MB), render page→JPEG, analyze_slide_vision, update + replace quiz. | backend/api/v1/ai_content.py:299; backend/services/ai/tutor_service.py:179 | Functioning | SSRF-guarded; uses HTTP/2 wrapper (ported in merge)
AI-17 | AI content gen | Deck-level quiz generation | Professor | As a professor, I want a cross-slide quiz spanning the deck. | POST /api/ai/decks/{id}/generate-quiz: summarize (≤12k), generate_deck_quiz requiring ≥2 linked_slides (repaired against concept map), persist anchored to first linked slide. | backend/api/v1/slides_ai.py:269; backend/services/ai/orchestrator.py:874 | Functioning | Unrepairable items dropped
AI-18 | AI content gen | Lecture & course descriptions | Professor | As a professor, I want AI-generated lecture and course descriptions. | POST /api/ai/lecture-description and /course-description (aggregates ≤4 summaries/lecture across course) via QUALITY_CHAIN. | backend/api/v1/ai_content.py:327; backend/services/ai/tutor_service.py:257 | Functioning | —
AI-19 | AI content gen | TTS narration | Student | As a student, I want spoken audio for AI text. | POST /api/ai/tts → generate_speech streams audio/mpeg. | backend/api/v1/ai_content.py:228 | Unclear | Endpoint exists; no frontend caller found
AI-20 | AI content gen | Model selection & failover | Any | As a user, I want my preferred model honored with automatic fallback. | ai_model literal → provider, moved to chain head, fails over (Cerebras→Groq→Cloudflare→Gemini…) with quota+429 backoff; unconfigured providers skipped. | backend/services/ai/orchestrator.py:543 | Partial | ai_content.py and slides_ai.py have divergent ai_model allow-lists — a model valid on one router is rejected on the other | Partial (confirmed) | ai_content._AiModelLiteral and slides_ai._AiModel diverged (slides_ai had unsupported 'deepseek'; ai_content had 'llama3' + lacked gemini-1.5/gpt-4o-mini) → a model accepted by one AI router rejected (422) by the other. | Low | Aligned both literals to orchestrator._USER_MODEL_TO_PROVIDER's 13 supported keys; dropped unsupported deepseek/llama3 (they silently fell back anyway; frontend only sends 4). | PASS (backend 638 green).
AI-21 | AI tutor | Tutor response without lecture scope | Student | As a student asking with no lecture context, I still get a response. | No lecture_id/pdf_hash/slide_index → retrieval skipped, prompt grounds only on slide_text; empty slide_text → ungrounded answer. LectureChat always passes lecture_id+slide_index. | backend/services/ai/tutor.py:152; backend/services/ai/retrieval.py:53 | Partial | No hard refusal anymore (refusal short-circuit removed); also orphaned dead code at tutor.py:122-125 | PASS (behavior change confirmed) | Out-of-scope refusal short-circuit was intentionally removed; the dead `return False/True` remnant caused the syntax error. Stale test test_tutor_grounding::test_out_of_scope_refusal_short_circuits_llm still asserts old behavior. | Low | Removed dead remnant (same as AI-01). Stale test to be reconciled.
MAP-01 | Mind map | View cached mind map | Any | As a viewer, I open a lecture and see its previously generated mind map. | GET /api/mind-map/{id} returns cached tree_data via RLS client; null if none; schema_version<2 treated stale (null+flag); frontend normalizes + caches 10min. | backend/api/v1/mind_map.py:44; src/features/mindmap/hooks/useMindMap.ts:14 | Functioning | GET + useQuery wired
MAP-02 | Mind map | Generate / regenerate mind map | Professor | As a professor, I AI-generate a knowledge tree from my lecture's slides. | POST /api/mind-map/{id}/generate (require_professor, 10/min) verifies ownership, loads ≤1000 slides, generate_mind_map, repairs tree (every real slide once, drops hallucinated/dupes), upserts schema_version=2. | backend/api/v1/mind_map.py:159; src/features/mindmap/hooks/useMindMap.ts:28 | Functioning | Ownership + AI + post-validate | PASS | mind_map endpoints import + tests green. | —
MAP-03 | Mind map | Generate gating in UI | Student | As a student, I cannot generate a mind map; I see the professor's or an empty state. | LectureView passes canGenerate = role==='professor'; MindMap shows generate only when canGenerate else 'professor has not generated' message; backend gates POST. | src/pages/LectureView.tsx:842; src/components/MindMap.tsx:392 | Functioning | Role-gated button + backend dep
MAP-04 | Mind map | Error/timeout handling on generate | Professor | As a professor, generation failures show a clear error not a hang. | Generate maps TimeoutError→504, others→502; GET failures→503; frontend logs onError. | backend/api/v1/mind_map.py:226 | Functioning | Explicit status mapping
MAP-05 | Concept graph | Ingest lecture concepts | Professor | As a professor, publishing a lecture extracts + links its concepts to the catalog. | POST /api/concepts/ingest/{id} (require_professor) ownership check then ingest_lecture_concepts: tags from blueprint+quiz, embed, match catalog via RPC/cosine, upsert concept_lecture links; auto-triggered from publish. | backend/api/v1/concepts.py:37; src/hooks/useLectureSubmit.ts:75 | Functioning | Embedding-based ingest + auto-trigger
MAP-06 | Concept graph | Student mastery vector | Student | As a student, I see my mastered vs weak concepts from quiz performance. | GET /api/concepts/student/{uid} returns {vector,mastered,weak} from compute_student_mastery; own vector only unless professor sharing course; KnowledgeMapCard renders lists. | backend/api/v1/concepts.py:64; src/components/KnowledgeMapCard.tsx:27 | Functioning | Mastery RPC + card
MAP-07 | Concept graph | Concepts for a lecture | Any | As a viewer, I see concepts tagged on a lecture. | GET /api/concepts/lecture/{id} (verify_token) owner-or-accessible-course check then concepts_for_lecture; powers RelatedAcrossCoursesPanel. | backend/api/v1/concepts.py:87; src/components/RelatedAcrossCoursesPanel.tsx:36 | Functioning | Access-checked concept list
MAP-08 | Concept graph | Related lectures across courses | Any | As a viewer, I jump to other lectures covering the same concept. | GET /api/concepts/{id}/related-lectures returns related_lectures_for_concept filtered to owned/accessible; panel lists clickable links + slide counts. | backend/api/v1/concepts.py:119; src/components/RelatedAcrossCoursesPanel.tsx:36 | Functioning | Result + accessibility filter
WRK-01 | Worksheets | List worksheets | Any | As an enrolled student or owning professor, I see files attached to a lecture. | GET /api/lectures/{id}/worksheets (verify_token) read-access check (owner OR course-enrolled OR assignment-enrolled), metadata newest-first; 404 if unauthorized. | backend/api/v1/worksheets.py:129 | Functioning | Access-gated list
WRK-02 | Worksheets | Upload worksheet | Professor | As a professor, I upload a PDF/doc/image to a lecture. | POST (require_professor, 20/min) MIME allowlist, 25MB via Content-Length + bounded read, insert row, upload to private worksheets bucket, rollback row on storage failure. | backend/api/v1/worksheets.py:167 | Functioning | MIME+size guard, transactional
WRK-03 | Worksheets | Rename worksheet | Professor | As a professor, I rename a worksheet. | PATCH /api/worksheets/{id} ownership check, update title, return refreshed. | backend/api/v1/worksheets.py:275 | Functioning | Owner-checked
WRK-04 | Worksheets | Delete worksheet | Professor | As a professor, I delete a worksheet + file. | DELETE ownership check, remove storage object (warn-continue on failure), delete row, 204. | backend/api/v1/worksheets.py:311 | Functioning | Owner-checked
WRK-05 | Worksheets | Download worksheet | Any | As an enrolled viewer, I get a working download link. | GET /download_url (verify_token) read-access check, 1-hour signed URL (fallback public), 404 if no file/access. | backend/api/v1/worksheets.py:347 | Functioning | Signed URL + access gate
WRK-06 | Practice sheets | List practice sheets | Any | As a student I see published sheets; as the professor I see all with counts. | GET /api/lectures/{id}/practice-sheets access-check; professor sees all (with question_count), students only status=published. | backend/api/v1/practice_sheets.py:159; src/features/practice_sheets/StudentPracticeSheetsPanel.tsx:26 | Functioning | Role-aware filtering
WRK-07 | Practice sheets | Create manual sheet | Professor | As a professor, I create a manual practice sheet (draft). | POST (require_professor) ownership check, insert kind=manual status=draft. | backend/api/v1/practice_sheets.py:207 | Functioning | Owner-checked
WRK-08 | Practice sheets | Auto-generate sheet from quizzes | Professor | As a professor, I auto-build a practice sheet from the lecture's quizzes. | POST /auto (10/min) requires slides+quiz_questions, creates/replaces single kind=auto sheet, maps each quiz to multiple_choice (correct_answer None-safe), links source_quiz_question_id. | backend/api/v1/practice_sheets.py:255 | Functioning | Errors 400 if no quizzes
WRK-09 | Practice sheets | View single sheet + questions | Any | As a viewer, I open a sheet and see questions. | GET /api/practice-sheets/{id}; students blocked unless published+accessible; returns sheet+questions. | backend/api/v1/practice_sheets.py:388 | Functioning | Published+access gate
WRK-10 | Practice sheets | Update sheet (title/publish) | Professor | As a professor, I rename and publish/unpublish a sheet. | PATCH created_by check, update title and/or status (validated draft¦published). | backend/api/v1/practice_sheets.py:427 | Functioning | Creator-checked, enum validated
WRK-11 | Practice sheets | Delete sheet | Professor | As a professor, I delete a practice sheet. | DELETE created_by check, delete, 204. | backend/api/v1/practice_sheets.py:463 | Functioning | Creator-checked
WRK-12 | Practice sheets | Add/edit/delete questions | Professor | As a professor, I author questions on a manual sheet. | POST/PATCH/DELETE questions check ownership; add rejects auto sheets (400), computes order_index; delete re-normalizes; types multiple_choice¦short_answer¦free_form. | backend/api/v1/practice_sheets.py:494 | Functioning | Manual-only add, reindex on delete
WRK-13 | Practice sheets | Reorder questions | Professor | As a professor, I reorder questions. | POST /reorder creator check, writes order_index by supplied position. | backend/api/v1/practice_sheets.py:634 | Functioning | Creator-checked
WRK-14 | Practice sheets | Submit attempt + auto-grade | Student | As a student, I submit answers and get a score. | POST /attempts; students only on published+accessible; _grade_attempt auto-grades multiple_choice + short_answer (case-insensitive exact), free_form excluded; stores score. | backend/api/v1/practice_sheets.py:668; src/features/practice_sheets/PracticeSheetTaker.tsx:90 | Partial | free_form not graded; short_answer exact-match only → all-free_form sheet scores 0.0
WRK-15 | Practice sheets | Professor preview attempts | Professor | As a professor, I preview a sheet without polluting analytics. | is_preview set only when caller is the professor + flag set; student-supplied flag ignored; preview excluded from /attempts/mine. | backend/api/v1/practice_sheets.py:712 | Functioning | Server-enforced preview flag
WRK-16 | Practice sheets | View own attempt history | Student | As a student, I see past attempts and scores. | GET /attempts/mine returns caller's non-preview attempts newest-first. | backend/api/v1/practice_sheets.py:748 | Functioning | Own-attempts query
WRK-17 | Assignments | List assignments (role-aware) | Any | As a professor I see my assignments with roster size; as a student only those I'm enrolled in, with status. | GET /api/assignments paginated; professor→own (with student_ids); student→assignment_enrollments membership with not_started/in_progress/completed/overdue computed from student_progress. | backend/api/v1/assignments.py:257 | Functioning | Role branch + status compute
WRK-18 | Assignments | View single assignment | Any | As an enrolled student or owner, I open one assignment with lectures + my status. | GET /{id} 404 if missing or not owner/enrolled (hides existence); owner gets student_ids, student gets status. | backend/api/v1/assignments.py:349 | Functioning | 404-hiding access gate
WRK-19 | Assignments | Create assignment | Professor | As a professor, I bundle lectures into an assignment with due date, min quiz score, roster. | POST verifies all lecture_ids owned, inserts assignment + assignment_lectures + optional assignment_enrollments (dedup); roster may be empty. | backend/api/v1/assignments.py:455 | Functioning | Ownership-verified create
WRK-20 | Assignments | Update assignment | Professor | As a professor, I edit title/desc/due/min-score/lectures/roster. | PATCH owner-checked; model_fields_set lets min_quiz_score null; replaces lecture join + roster wholesale; re-verifies lecture ownership. | backend/api/v1/assignments.py:509 | Functioning | Owner-checked partial update
WRK-21 | Assignments | Delete assignment | Professor | As a professor, I delete an assignment. | DELETE owner-checked, cascade clears joins, 204. | backend/api/v1/assignments.py:576 | Functioning | Owner-checked
WRK-22 | Assignments | Enrollable students picker | Professor | As a professor, I pick from students I've actually taught. | GET /_meta/students returns id+full_name (email omitted) for students with progress on my lectures. | backend/api/v1/assignments.py:383 | Functioning | Scoped, PII-minimized
WRK-23 | Assignments | Completion model (no submission entity) | Student | As a student, I 'submit' implicitly by completing lectures/quizzes. | compute_status_for_user: completion from student_progress completed_at + quiz_score>=min_quiz_score; no upload/manual grading; 'completed' beats 'overdue'. | backend/api/v1/assignments.py:111 | Functioning | Progress-derived (by design)
WRK-24 | Assignments | Student dashboard CTA into work | Student | As a student, I see status pill + progress bar + button into the first incomplete lecture. | AssignmentsPanel lists assignments with status label/color/icon, builds progressByLecture from dashboard.progress, navigates into first incomplete lecture. | src/features/assignments/AssignmentsPanel.tsx:66 | Functioning | Panel + CTA
DSH-01 | Student dashboard | Dashboard load & data fetch | Student | As a student, I open my dashboard and see lectures, courses, progress, achievements, visits. | useStudentDashboard runs 5 react-query queries; skeleton while loading, error card+Retry on error, refreshes profile + subscribes realtime student_progress to invalidate progress. | src/features/student/hooks/useStudentDashboard.ts:18; src/pages/StudentDashboard.tsx:54 | Functioning | Granular queries + realtime + states
DSH-02 | Student dashboard | Hero stage + media rail | Student | As a student, I see a cinematic hero for a focused lecture and a navigable rail of all lectures. | selectHero picks resume/next/review/onboard; MediaRail renders all; focus clamps to hero id; CTA label Start/Continue/Review/Browse by status; launch opens lecture. | src/pages/StudentDashboard.tsx:68; src/features/student/homeFeed.ts:116 | Functioning | selectHero + HeroStage + MediaRail
DSH-03 | Student dashboard | Bento widgets | Student | As a student, I see streak, level/XP, trophy count + recent achievements, up-next, per-course progress. | buildWidgets always pushes streak+trophies; adds upNext (uncompleted exists) + courseProgress (overall %). | src/features/student/homeFeed.ts:232; src/pages/StudentDashboard.tsx:342 | Functioning | Widgets from profile+achievements+progress
DSH-04 | Student dashboard | Quiz accuracy display | Student | As a student, my overall quiz accuracy is shown on the hero. | accuracy = round(correct/answered*100) across progress rows; passed to HeroStage + ReviewCelebration. | src/pages/StudentDashboard.tsx:98 | Functioning | Pure derivation
DSH-05 | Student dashboard | Recently viewed (lectures+courses) | Student | As a student, I see a deduped recency-ordered mix of recently viewed lectures and courses. | buildRecentlyViewed combines lectures+courseVisits, excludes hero + continue-rail ids; click opens lecture or course. | src/pages/StudentDashboard.tsx:82; src/features/student/homeFeed.ts:385 | Functioning | Wired with dedupe
DSH-06 | Student dashboard | Browse rows (Continue + per-course) | Student | As a student, I see Netflix-style rows: Continue Learning + one per course, recency-ordered. | buildRows uses courseVisits for ordering; rows via BrowseRow, each opening a lecture. | src/pages/StudentDashboard.tsx:74; src/features/student/homeFeed.ts | Functioning | buildRows rendered
DSH-07 | Student dashboard | Recency tracking on open | Student | As a student, opening a lecture records lecture + course visit. | openLecture fires recordLectureVisit + recordCourseVisit fire-and-forget then navigates. | src/pages/StudentDashboard.tsx:128 | Functioning | Non-blocking writes
DSH-08 | Student dashboard | Daily activity + streak banner | Student | As a student, my daily visit is recorded and a streak banner appears when streak>2. | useEffect recordDailyActivity then gamification.evaluate(); banner for STREAK_BANNER_DURATION_MS when current_streak>2. | src/pages/StudentDashboard.tsx:141 | Functioning | Threshold hardcoded >2
DSH-09 | Student dashboard | Onboard/review/full-feed adaptation | Student | As a new student I get a focused start panel; when done a celebration; else full feed. | heroKind drives layout: onboard→OnboardPanel only; review→ReviewCelebration above rails; else full bento/rows/insights. | src/pages/StudentDashboard.tsx:88; src/features/student/components/OnboardPanel.tsx:12 | Functioning | heroKind branch
DSH-10 | Student dashboard | Quick-check micro-quiz | Student | As a student with an in-progress lecture, I see a quick-check micro-quiz near my last slide. | MicroQuizCard for continueLectures[0] with targetSlideNumber=max(1,last_slide_viewed-1). | src/pages/StudentDashboard.tsx:359 | Functioning | Conditional on continueLectures[0]
DSH-11 | Student dashboard | Insights teaser + knowledge map | Student | As a student, I click an insights teaser to open Learning Insights and view my Knowledge Map. | Clickable/keyboard card navigates INSIGHTS; KnowledgeMapCard rendered. | src/pages/StudentDashboard.tsx:382 | Functioning | role=button + Enter/Space
DSH-12 | Student dashboard | Below-fold deferral | Student | As a student, heavy below-fold widgets mount only after entrance animation (~380ms). | showBelowFold gated by setTimeout 380ms; all below-fold gated on it. | src/pages/StudentDashboard.tsx:50 | Functioning | Deferred mount
NDG-01 | Nudges | Daily nudge banner display | Student | As a student, I see a single highest-priority unread nudge as a dismissible banner. | NudgeBanner queries notifications read=false type in (streak,assignment,review), sorts priority desc then created_at, shows top. | src/components/NudgeBanner.tsx:38 | Functioning | Query + defensive sort
NDG-02 | Nudges | Open nudge deep link | Student | As a student, clicking Open navigates to the nudge's deep link. | open() → top.deep_link or FALLBACK_DEEP_LINK_BY_TYPE[type] or /dashboard. | src/components/NudgeBanner.tsx:99 | Functioning | deep_link + per-type fallback
NDG-03 | Nudges | Dismiss nudge + quiet period | Student | As a student, dismissing a nudge hides it and prevents reappearing during a quiet window. | Optimistic hide then POST /api/nudges/{id}/dismiss; backend dismissed=true, extends quiet_until by per-rule days, marks read. | src/components/NudgeBanner.tsx:84; backend/services/nudge_engine.py:499 | Functioning | Per-rule cool-off (streak1/assignment2/review14)
NDG-04 | Nudges | Streak-at-risk rule | Student | As a student with a streak who hasn't acted today, I get a 'don't lose your streak' nudge. | StreakAtRiskRule fires only when current_streak>=1 and last activity exactly yesterday (UTC). | backend/services/nudge_engine.py:96 | Functioning | Boundary-exact
NDG-05 | Nudges | Assignment-due-soon rule | Student | As a student, I get a nudge per enrolled assignment due within 2 days and not done. | AssignmentDueSoonRule iterates within window_days(2), skips completed/overdue, priority 90 if due today else 70. | backend/services/nudge_engine.py:138 | Functioning | Status via compute_status_for_user
NDG-06 | Nudges | Weak-concept-stale rule | Student | As a student, I get a review nudge for a low-mastery concept untouched 14+ days. | WeakConceptStaleRule fires for mastery<0.5 and updated_at older than 14 days, oldest-first. | backend/services/nudge_engine.py:183 | Functioning | Thresholds constants
NDG-07 | Nudges | Daily runner (fan-out) | Admin | As the system, a daily job evaluates active users and emits nudges idempotently. | run_daily loads users active last 30 days, builds context, evaluates rules, inserts notifications + upserts nudge_dismissals quiet_until; idempotent within quiet window. | backend/services/nudge_engine.py:279 | Functioning | Idempotency via (user,rule,subject)
NDG-08 | Nudges | Scheduler enablement | Admin | As an operator, the daily nudge job runs on cron only when enabled. | nudge_scheduler runs CronTrigger at NUDGE_RUN_HOUR_UTC (13:00) only when ENABLE_NUDGE_SCHEDULER==1; off in dev/tests. | backend/main.py:169; backend/services/nudge_scheduler.py:25 | Partial | Disabled by default; no nudges fire unless env flag set
NDG-09 | Nudges | Manual run trigger | Admin | As an external scheduler, I POST /api/nudges/run with a shared secret to trigger the job. | run_engine gated by X-Nudge-Run-Secret == NUDGE_RUN_SECRET; 404 if secret unset, 401 if mismatch. | backend/api/v1/nudges.py:57 | Functioning | Shared-secret gate
NDG-10 | Planner | Personalized study plan API | Student | As a student, I fetch a per-day plan sequencing assignments, weak-concept reviews, continue-where-left-off. | GET /api/schedule/me builds plan: assignments (hard, spread to due), weak concepts (soft, ≤3), in-progress filler; honors daily budget; degrades gracefully. | backend/api/v1/schedule.py:33; backend/services/scheduler.py:199 | Functioning | Pure build_plan + thin assembly
NDG-11 | Planner | Mark plan item done | Student | As a student, I mark a plan item complete; it's suppressed for a cooldown. | POST /api/schedule/items/{id}/done upserts schedule_item_completions idempotently; assemble_user_state suppresses recent completions (3-day cooldown). | backend/api/v1/schedule.py:56; backend/services/scheduler.py:530 | Functioning | Cross-day suppression
NDG-12 | Planner | Study plan UI card | Student | As a student, I see a 'Your Study Plan' card with today + upcoming days, mark-done, slide deep links. | OptimalScheduleCard fetches /api/schedule/me?days=7, renders DaySection/ItemRow, markDone optimistic; empty/error fallbacks. | src/components/OptimalScheduleCard.tsx:185 | Broken | Component fully implemented but NEVER imported/rendered anywhere — planner UI unreachable | BROKEN (confirmed) | OptimalScheduleCard fully built but zero render sites → planner UI unreachable. | Medium | Mounted <OptimalScheduleCard/> in StudentDashboard below-fold after KnowledgeMapCard (+ import). | PASS (tsc clean; mounted). Browser confirm needs auth.
NDG-13 | Planner | Per-user daily study budget | Student | As a student, my plan respects my daily study-minute budget. | get_daily_budget_minutes reads profiles.study_minutes_per_day, falls back to 30. | backend/services/scheduler.py:565 | Partial | Backend honors it but no UI to set study_minutes_per_day
ONB-01 | Onboarding | Name + avatar capture | Student | As a new student, I enter my name (step 1) and pick/upload an avatar (step 2). | Step1 name required to advance; Step2 preset avatars or custom upload to avatars bucket (image-only, <2MB). | src/pages/Onboarding.tsx:339 | Functioning | File-type + 2MB guards
ONB-02 | Onboarding | Academic fingerprint | Student | As a new student, I select university→faculty→program→semester via cascading dropdowns. | Step3 getUniversities/getFaculties/getDegreePrograms RPCs; cascades reset children; single options auto-selected; email-domain pre-select of university. | src/pages/Onboarding.tsx:401; src/services/academicService.ts:33 | Functioning | Cascade + domain pre-select
ONB-03 | Onboarding | No-catalog fallback | Student | As a student whose university has no catalog, I enter my institution as free text. | noCatalog branch shows free-text input; handleNext skips confirm; on finish saves via setMySocialProfile. | src/pages/Onboarding.tsx:419 | Functioning | hasCatalog flag drives branch
ONB-04 | Onboarding | Confirm suggested courses | Student | As a student, I confirm/adjust pre-populated courses with status completed/taking-now/planned. | Step4 getSuggestedCourses(programId,semester); pre-checks suggested; toggle inclusion + status; counts shown. | src/pages/Onboarding.tsx:478; src/services/academicService.ts:63 | Functioning | RPC + statusMap
ONB-05 | Onboarding | Extra platform course enrollment | Student | As a student, I optionally select extra platform courses to enroll. | Step5 browseCourses list, multi-select, enrollInCourse per selection on finish. | src/pages/Onboarding.tsx:545 | Functioning | Per-course enroll (errors non-fatal)
ONB-06 | Onboarding | Finish: persist all | Student | As a student, finishing saves profile, academic profile, courses, enrollments, verifies institution, awards badges. | handleFinish updates profiles, setAcademicProfile, confirmCatalogCourses, enroll loop, verifyMyInstitution (best-effort), gamification.evaluate, hard-redirect /dashboard. | src/pages/Onboarding.tsx:242 | Functioning | Sequential awaits; verify non-fatal
ONB-07 | Onboarding | University email linking | Student | As a student, I link my institutional email to verify my university by domain. | UniversityEmailLink shown when a university selected; linkUniversityEmail RPC returns verified/reason. | src/pages/Onboarding.tsx:462; src/services/academicService.ts:161 | Functioning | RPC link_university_email + verify
ONB-08 | Academic | Catalog scraper admin controls | Admin | As an admin, I trigger a catalog scrape/ingest and view per-source freshness. | POST /api/admin/academic/scrape (role=admin, 2/hour, synchronous); GET /sources returns last_scraped_at + faculty/course counts. | backend/api/v1/academic.py:32; src/services/academicService.ts:207 | Functioning | Admin-gated; synchronous (no queue yet)
ONB-09 | Recommendations | Personalized course recommendations | Student | As a student, I see platform courses recommended from my academic fingerprint with a reason and score. | getRecommendedCourses → get_recommended_courses RPC (excludes enrolled); rendered in CourseCatalogSheet. | src/services/academicService.ts:124; src/features/student/components/CourseCatalogSheet.tsx:38 | Partial | Surfaced only in library catalog sheet, not on dashboard
ONB-10 | Academic | Edit academic profile post-onboarding | Student | As a student, I later edit university/program/semester and re-confirm courses from settings. | AcademicProfileEditor reuses academic RPCs; Settings explains it unlocks classmate suggestions/recs/rankings. | src/components/AcademicProfileEditor.tsx:5; src/pages/Settings.tsx:391 | Functioning | Editor wired to same RPCs
GAM-01 | Gamification | Earn XP for correct answers | Student | As a student, answering correctly earns XP so my total rises. | grantXp(10,'quiz_correct'); grant_xp RPC inserts xp_event, adds to total_xp, recomputes current_level=floor(xp/100)+1; profile refreshed. | src/pages/LectureView.tsx:495; supabase/migrations/20260616000000_gamification_engine.sql:118 | Functioning | Wired + server RPC
GAM-02 | Gamification | One-time lecture-completion XP | Student | As a student, finishing a lecture grants +20 XP once. | grantXp(20,'lecture_complete','lecture:<id>'); dedupe_key unique index makes idempotent. | src/pages/LectureView.tsx:665; migrations/20260616000000:36 | Functioning | dedupe_key unique index
GAM-03 | Gamification | Earn streak badges (On Fire/Unstoppable) | Student | As a student, 5 then 10 correct in a row awards a badge with popup. | correctStreakRef 5→awardBadge('On Fire'), 10→'Unstoppable'; award_badge RPC inserts achievement, grants XP, notification, returns def; refuses state badges. | src/pages/LectureView.tsx:499; migrations/20260616000000:219 | Functioning | Event-badge RPC + popup queue
GAM-04 | Gamification | Earn 'First Quiz Completed' badge | Student | As a student, completing my first lecture quiz awards a badge. | On complete awardBadge('First Quiz Completed') (metric NULL=event); idempotent via achievements unique (user,badge). | src/pages/LectureView.tsx:666; migrations/20260616000000:31 | Functioning | Event badge
GAM-05 | Gamification | Earn 'Voice Heard' for feedback | Student | As a student, submitting feedback awards a badge. | FeedbackWidget calls awardBadge('Voice Heard') after submit. | src/components/FeedbackWidget.tsx:64; migrations/20260616000000:100 | Functioning | Event badge
GAM-06 | Gamification | Server sweep awards state badges | Student | As a student, after actions any newly-qualified threshold badge auto-awards. | evaluate() debounces 400ms then evaluate_badges RPC derives metrics from durable tables, grants each met threshold; newly-awarded returned for popups. | src/lib/gamification/GamificationProvider.tsx:116; migrations/20260616000000:249 | Functioning | Server-authoritative sweep
GAM-07 | Gamification | Evaluate after key actions | Student | As a student, badges re-check after lectures, quizzes, tutor, profile edits, onboarding, email verify. | gamification.evaluate() invoked from dashboard, lecture view, micro-quiz, chat, email link, settings, onboarding, academic editor. | src/pages/StudentDashboard.tsx:157; src/components/LectureChat.tsx:262 | Functioning | Broad call-site coverage
GAM-08 | Gamification | Badge-earned popup | Student | As a student, earning a badge shows a celebration modal. | onAwarded queues items; BadgeEarnedModal for queue head kind==='badge'; label localized via badgeLabel. | src/lib/gamification/GamificationProvider.tsx:104; src/components/BadgeEarnedModal.tsx | Functioning | Modal from queue
GAM-09 | Gamification | Level-up popup | Student | As a student, crossing a level shows a level-up modal once per level/device. | Effect watches current_level, fires LevelUpModal above max(lastLevel, persisted level); persists ceiling in localStorage. | src/lib/gamification/GamificationProvider.tsx:76 | Functioning | localStorage de-dupe
GAM-10 | Gamification | Bundled badge XP once | Student | As a student, a badge with XP reward adds that XP once. | _grant_badge calls grant_xp(xp_reward,'badge:<key>','badge:<key>'); dedupe key prevents double. | migrations/20260616000000:200 | Functioning | Dedupe via badge key
GAM-11 | Gamification | Achievement notification | Student | As a student, earning a badge creates an in-app notification. | _grant_badge inserts notifications (type achievement) with name+description. | migrations/20260616000000:205 | Functioning | Notification insert
GAM-12 | Gamification | View earned + locked (Achievements page) | Student | As a student, I view earned badges plus a 'Potential Milestones' list. | Fetches achievements for user; locked list filters a hard-coded possibleAchievements array by earned names. | src/pages/Achievements.tsx:39 | Partial | Locked list is stale hard-coded array, not DB catalog; duplicates Ascent Trophies tab | Partial (confirmed) | Achievements.tsx locked 'Potential Milestones' built from a hard-coded possibleAchievements array, not the DB badge_definitions catalog → drifts from real catalog (Ascent.tsx does it right). | Low | Refactored Achievements.tsx to fetchBadgeCatalog() and derive locked = catalog minus earned (by name) minus is_secret. Removed the hard-coded array. | PASS (tsc clean; vitest 219).
GAM-13 | Gamification | Badge catalog (Ascent Trophies) | Student | As a student, the Ascent Trophies tab shows earned + locked badges by category from the DB catalog. | fetchBadgeCatalog reads badge_definitions; locked = catalog minus earned (excl secret), grouped by category; shows +XP. | src/pages/Ascent.tsx:602; src/services/gamificationService.ts:74 | Functioning | DB-catalog-driven
GAM-14 | Gamification | XP progress + stats | Student | As a student, I see total XP, level, current/best streak, earned count. | XPProgress + stat cards read profile fields + achievements.length. | src/pages/Achievements.tsx:97; src/pages/Ascent.tsx:459 | Functioning | Profile-driven
GAM-15 | Gamification | Achievements localization mismatch | Student | As a student, earned-badge titles should display cleanly. | Ascent maps badge_name through badgeLabel; Achievements page shows raw badge_name with no i18n. | src/pages/Achievements.tsx:194; src/pages/Ascent.tsx:576 | Partial | Achievements.tsx shows raw key text | Partial (confirmed) | Achievements.tsx rendered raw English badge_name (no i18n), unlike Ascent.tsx (badgeLabel). | Low | Localized earned + locked badge names via badgeLabel(t, def), resolving each earned row's catalog key by name. | PASS (tsc clean; vitest 219).
GAM-16 | Gamification | Legacy add_xp_to_user wrapper | Any | As a legacy caller, add_xp_to_user still adds XP. | Thin wrapper delegates to grant_xp(p_xp,NULL,NULL). | migrations/20260616000000:162 | Functioning | Back-compat wrapper
RNK-01 | Ranks | 7-tier rank from total XP | Any | As a user, my total XP maps to a rank tier (Newcomer→Immortal). | rankForXp clamps XP>=0, returns highest tier met; thresholds 0/500/1500/3500/7000/13000/25000. | src/lib/rank.ts:31 | Functioning | Pure resolver
RNK-02 | Ranks | Rank ring on avatar | Any | As a user, my avatar border reflects my rank with gradient/glow; top tiers animate. | RankRing renders padding-box gradient ring; glow per tier; Legend/Immortal rotating conic (halted under reduced-motion). | src/components/RankRing.tsx:21 | Functioning | Safari-safe ring
RNK-03 | Ranks | Rank ring in profile chip | Any | As a user, my sidebar profile chip avatar shows my rank ring. | ProfileChip computes rankForXp(total_xp), wraps avatar in RankRing md. | src/components/console/ProfileChip.tsx:41 | Functioning | Profile-driven
RNK-04 | Ranks | Rank ring on social avatars | Any | As a user, avatars across social surfaces show each person's rank ring. | atoms Avatar resolves tier from rankForXp(totalXp), wraps in RankRing. | src/features/social/components/atoms.tsx:32 | Functioning | Used in lists/profiles
RNK-05 | Ranks | Rank progress to next tier | Any | As a user, progress within my tier + XP-to-next is computable. | rankProgress returns tier,next,toNext,pct (1.0 at max). | src/lib/rank.ts:56 | Functioning | Pure helper
SOC-01 | Social | View friends hub | Student | As a student, I see my friends, who's active now, and pending requests. | FriendsHub uses useFriends + useFriendRequests; online (active_today) row, all-friends list, incoming preview; empty CTA to Find friends. | src/features/social/pages/FriendsHub.tsx:9; migrations/20260613000000_social_friends.sql:315 | Functioning | get_friends RPC
SOC-02 | Social | Send a friend request | Student | As a student, I send a friend request; a reciprocal pending auto-accepts. | FriendButton 'Add friend' → send_friend_request; RPC auto-accepts reciprocal pending else upserts pending outgoing (no self-friend). | src/features/social/components/FriendButton.tsx:44; migrations/20260613000000:229 | Functioning | Reciprocal auto-accept
SOC-03 | Social | Accept / decline request | Student | As a student, I accept or decline incoming requests. | Accept/Decline → respond_friend_request(requester,bool); sets accepted/declined; toast; cache invalidated. | src/features/social/pages/FriendRequests.tsx:62; migrations/20260613000000:262 | Functioning | RPC + invalidation
SOC-04 | Social | Cancel outgoing request | Student | As a student, I cancel a pending request I sent. | Cancel / FriendButton 'Pending' → cancel_friend_request deletes my pending outgoing edge. | src/features/social/components/FriendButton.tsx:37; migrations/20260613000000:281 | Functioning | Delete pending edge
SOC-05 | Social | Remove a friend | Student | As a student, I unfriend someone. | removeFriend → remove_friend deletes accepted edge either direction; mutation exists, no dedicated remove button in audited pages. | src/features/social/hooks.ts:80; migrations/20260613000000:297 | Partial | RPC+mutation wired; no visible remove-friend UI
SOC-06 | Social | Requests with affinity | Student | As a student, request cards show mutual friends, shared courses, verified badge. | FriendRequests tabs by direction; cards show mutualFriends, sharedCourses/mutualCourses, institutionVerified from get_friend_requests. | src/features/social/pages/FriendRequests.tsx:43; migrations/20260615000400_friend_requests_verified.sql:10 | Functioning | Enriched request RPC
SOC-07 | Social | Find / search friends | Student | As a student, I search learners by name/institution, filter by role + shared courses. | FindFriends debounces, search_users (excludes self, students only, optional common-courses); institution options from results. | src/features/social/pages/FindFriends.tsx:44; migrations/20260615000200_academic_personalization.sql:30 | Functioning | Academic-aware search
SOC-08 | Social | Friend suggestions | Student | As a student, when not searching I see suggested peers from my courses/program/semester. | useFriendSuggestions(8) → get_friend_suggestions ranked by affinity; shown only with no query/filters. | src/features/social/pages/FindFriends.tsx:65; migrations/20260615000200:95 | Functioning | Affinity-ranked
SOC-09 | Social | View another user's profile | Student | As a student, I open a learner's profile to see stats, mutuals, courses, and act. | FriendProfile uses get_user_profile + get_user_courses; gates live activity + courses behind friendship; FriendButton or Accept/Decline; redirects to own if me. | src/features/social/pages/FriendProfile.tsx:14; migrations/20260613000000:431 | Functioning | Friend-gated profile
SOC-10 | Social | View / edit my social profile | Student | As a student, I view my profile and edit institution + social roles. | SocialProfile shows me, friends, courses, weekly XP chart; editor saves via set_my_social_profile (XP/level locked). | src/features/social/pages/SocialProfile.tsx:16; migrations/20260613000000:21 | Functioning | Own-row social update
SOC-11 | Social | Global leaderboard with podium | Student | As a student, I see a ranked leaderboard with my rank and reward. | useGlobalLeaderboard → get_global_leaderboard; client sorts by weekly/total XP, computes rank/reward (5%); podium top-3 + table. | src/pages/Leaderboard.tsx:14; migrations/20260615000200:150 | Functioning | Students-only, XP-ranked
SOC-12 | Social | Leaderboard cohort filters | Student | As a student, I filter leaderboard by university/faculty/semester/verified. | Client-side filters over fetched rows from academic-aware RPC. | src/pages/Leaderboard.tsx:26 | Functioning | Client-side filters
SOC-13 | Social | Leaderboard period labels | Student | As a student, I toggle leaderboard period. | Toggle labeled 'Daily'/'Monthly' but maps to period 'week'(last 7d)/'all'(all-time). | src/pages/Leaderboard.tsx:86 | Partial | Labels don't match week/all-time semantics | Partial (confirmed) | Leaderboard period toggle labeled 'Daily'/'Monthly' but mapped to week(last-7d)/all(all-time). | Low | Relabeled buttons 'This Week' / 'All Time' to match the underlying period semantics (logic unchanged). | PASS (tsc clean).
SOC-14 | Social | Weekly XP chart | Student | As a student, my profile shows a 7-day XP bar chart. | WeeklyXpChart uses get_weekly_xp_by_day (7 rows) as bars. | src/features/social/pages/SocialProfile.tsx:122; migrations/20260613000000:131 | Functioning | 7-day RPC
SOC-15 | Social | Friend button states | Student | As a student, the friend button reflects friends/incoming/pending/none. | FriendButton renders Friends/Awaiting you/Pending(cancel)/Add friend per relationship_status RPC. | src/features/social/components/FriendButton.tsx:8; migrations/20260613000000:184 | Functioning | relationship_status RPC
SOC-16 | Social | Demo network bootstrap | Student | As a student, a one-click action could seed a demo friend network. | bootstrap_demo_friends RPC + api + mutation exist, but no UI invokes them. | src/features/social/hooks.ts:85; migrations/20260613000000:514 | Partial | Dead path — no call site
SOC-17 | Social | Self vs others routing | Student | As a student, visiting my own /profile/:id redirects to my profile page. | FriendProfile redirects to PROFILE when userId===me.id. | src/features/social/pages/FriendProfile.tsx:23 | Functioning | Self-redirect guard
ANL-01 | Prof analytics | Lecture picker (Insight Garden entry) | Professor | As a professor, I pick one of my courses/lectures to view its analytics. | ProfessorAnalytics resolves URL param (uuid/slug) against my own lectures+courses, renders GardenLecturePicker, navigates to /professor/analytics/:slug. | src/pages/ProfessorAnalytics.tsx:21 | Functioning | Real: per-userId fetch
ANL-02 | Prof analytics | Insight Garden feed | Professor | As a professor, I get a ranked feed of plain-language insights about my lecture. | InsightGarden useInsights → GET /analytics/lecture/{id}/insights → get_lecture_insights → build_insights; top-attention banner, 4 cards at rest + 'show all', skeletons, error, HealthyEmptyState. | src/features/analytics/garden/InsightGarden.tsx:11; backend/api/v1/analytics.py:244 | Functioning | Real: detector engine
ANL-03 | Prof analytics | Insight detection engine | Professor | As a professor, I want insights derived from real student behavior. | 11 pure detectors over a per-lecture bundle (confusion_hotspot, overpacked, silent_strugglers, leaky_bucket, etc.), gated by min-sample, severity-ranked. | backend/services/insights/detectors.py:59 | Functioning | Real thresholds over signals
ANL-04 | Prof analytics | Insight ownership enforcement | Professor | As a professor, I only see analytics for lectures I own. | Every /lecture/{id}/* calls _assert_lecture_owner (404/403); course endpoints _assert_course_owner. | backend/api/v1/analytics.py:148 | Functioning | Ownership per endpoint
ANL-05 | Adv analytics | Drill-down dashboard | Professor | As a professor, I want a comprehensive advanced dashboard per lecture. | AdvancedAnalytics useAnalytics → GET /lecture/{id}/dashboard (get_dashboard_data single SQL call) → overview, slidePerformance, studentsMatrix, dropoff, confidence, retry, activityByDay. | src/pages/AdvancedAnalytics.tsx:543; backend/api/v1/analytics.py:230 | Functioning | Real aggregated SQL
ANL-06 | Adv analytics | Per-slide recommendations | Professor | As a professor, each slide is flagged with a recommendation + reasons. | SlideRecommendationsSection table of slide#/title/views/dropoff%/confusion%/quiz + recommendation_label + reasons; computed in get_slide_analytics. | src/pages/AdvancedAnalytics.tsx:303; backend/services/analytics_service.py:134 | Functioning | Real per-slide metrics
ANL-07 | Adv analytics | Most-missed questions (retry) | Professor | As a professor, questions ranked by first vs second-attempt miss rate. | retryPerformance from get_retry_performance / _calculate_retry_performance. | src/pages/AdvancedAnalytics.tsx:1097; backend/services/analytics_service.py:425 | Functioning | Real from quiz attempts
ANL-08 | Adv analytics | Where students quit (drop-off) | Professor | As a professor, I see which slide non-completers abandon on. | dropoffData from GET /lecture/{id}/dropoff (get_dropoff_map uses last_slide_viewed for non-completers). | src/pages/AdvancedAnalytics.tsx:1162; backend/services/analytics_service.py:513 | Functioning | Real
ANL-09 | Adv analytics | Confidence by slide | Professor | As a professor, a per-slide got-it/unsure/confused breakdown. | confidenceBySlide from GET /lecture/{id}/confidence-by-slide (get_confidence_by_slide). | src/pages/AdvancedAnalytics.tsx:1197; backend/services/analytics_service.py:562 | Functioning | Real
ANL-10 | Adv analytics | Student matrix / typology | Professor | As a professor, students bucketed by behavioral typology with progress/score/AI/revisions. | studentsMatrix with typology by calculate_student_typology (Disengaged/At-Risk, Reviser, Natural, Struggling, Standard); names via generate_anon_name. | src/pages/AdvancedAnalytics.tsx:1258; backend/services/analytics_service.py:972 | Functioning | Real, anonymized; rule-based (not 'archetype/triad' naming)
ANL-11 | Adv analytics | Interaction velocity | Professor | As a professor, event density over last 7 days. | activityByDay (7-day generate_series LEFT JOIN learning_events quiz_attempt) as area chart. | src/pages/AdvancedAnalytics.tsx:1228; backend/services/analytics_service.py:699 | Functioning | Real
ANL-12 | Adv analytics | Student questions feed | Professor | As a professor, I read the actual questions students asked the AI tutor. | aiQueryFeed from GET /lecture/{id}/ai-queries (get_ai_query_feed over ai_tutor_query events). Subtitle 'Grouped by similarity' but backend returns flat chronological. | src/pages/AdvancedAnalytics.tsx:1400; backend/api/v1/analytics.py:311 | Partial | Real data but 'grouped by similarity' label is cosmetic/unimplemented | Partial (confirmed) | Student Questions Feed subtitle said '(Grouped by similarity)' but backend returns flat chronological — false claim. | Low | Relabeled to '(most recent first)' to match actual behavior. | PASS (tsc 0).
ANL-13 | Adv analytics | Per-metric AI interpretation | Professor | As a professor, I click a metric and get an AI explanation. | handleMetricClick POSTs /api/ai/metric-feedback; cached per metric; failure shows 'Could not establish neural link'. | src/pages/AdvancedAnalytics.tsx:598 | Functioning | Real AI call + fallback
ANL-14 | Adv analytics | Ask Your Data (per-lecture NL) | Professor | As a professor, I ask NL questions about a lecture's analytics. | AskYourDataPanel POSTs /lecture/{id}/ask (ask_lecture_data): LLM picks fixed intent, server runs matching fn (no raw SQL), returns answer/table/chart + suggestions; 20/min. | src/pages/AdvancedAnalytics.tsx:961; backend/api/v1/analytics.py:515 | Functioning | Real intent-constrained LLM
ANL-15 | Adv analytics | Comparative benchmarks | Professor | As a professor, I compare a lecture against siblings in the same course. | BenchmarksSection → GET /lecture/{id}/benchmarks + /course/{id}/benchmarks; ownership-enforced. | src/pages/AdvancedAnalytics.tsx:964; backend/api/v1/analytics.py:686 | Functioning | Real aggregated siblings
ANL-16 | Prof analytics | Hidden/disabled panels | Professor | As a professor, certain experimental panels are intentionally hidden. | SHOW_PREDICTIVE_INTERVENTION_HUB + SHOW_SPATIAL_NEURAL_MATRIX hardcoded false. | src/pages/AdvancedAnalytics.tsx:539 | Partial | Feature-flagged off in code
ANL-17 | Prof analytics | Distractor analysis | Professor | As a professor, I see which wrong option students pick most per question. | GET /lecture/{id}/distractors (get_distractor_analysis) returns answer_distribution + most_common_wrong_answer; owner-guarded. | backend/api/v1/analytics.py:260; backend/services/analytics_service.py:363 | Unclear | Backend real; no clear consuming component found in render scan
ANL-18 | Prof analytics | Course-wide overview (dashboard) | Professor | As a professor, I see whole-course aggregates with a course selector. | ProfessorOverviewSection (on ProfessorDashboard) useProfessorOverview → GET /analytics/professor/overview; weakest_concepts degrades to weakest_slides if graph empty; 60/min. | src/features/analytics/components/ProfessorOverviewSection.tsx:13; backend/api/v1/analytics.py:345 | Functioning | Real cached aggregate
ANL-19 | Prof analytics | Refresh analytics cache | Professor | As a professor, I force-refresh stale analytics. | POST /lecture/{id}/cache/refresh + /course/{id}/cache/refresh invalidate + warm-recompute; return invalidated_rows + recomputed. | backend/api/v1/analytics.py:376 | Functioning | Real invalidation
ANL-20 | Prof analytics | Professor-wide Ask / Chat | Professor | As a professor, I ask/chat in NL across all my courses/lectures. | POST /professor/ask (intent-constrained) + /professor/chat (conversational, grounded in real courses/lectures); chat capped 50 msgs; rate-limited. | backend/api/v1/analytics.py:597; src/features/analytics/components/useProfessorChat.ts | Functioning | Real grounded LLM
ANL-21 | Student analytics | Personal optimal study schedule | Student | As a student, I learn my best time to study from history. | GET /analytics/personal/optimal-schedule (get_personal_optimal_schedule) analyzes peak-performance windows; accepts timezone_offset. | backend/api/v1/analytics.py:725; backend/services/analytics_service.py:1662 | Functioning | Real from event history
ANL-22 | Student insights | Learning Insights page | Student | As a student, I want plain-language insights about my own learning. | Insights page derives accuracy/lecturesDone/coursesStarted from useStudentDashboard + narrative cards; INSIGHTS route redirects to ASCENT (reached via Intelligence Center tabs). | src/pages/Insights.tsx:135; src/App.tsx:278 | Partial | Real metrics but canned headlines/tips; /insights route redirected away
ADM-01 | Admin | Access guard | Admin | As an admin, only I can open the admin dashboard. | /admin/dashboard ProtectedRoute allowedRoles=['admin']; require_admin guards every /api/admin endpoint; admins redirected to /admin/dashboard on login. | src/App.tsx:412; backend/api/v1/admin.py:27 | Functioning | Role-gated front+back
ADM-02 | Admin | User auditing (Activity Tracker) | Admin | As an admin, I see all users with roles, XP/level, signup date. | GET /api/admin/users (raw SQL profiles + json_agg user_roles) renders a table; roles display-only — no edit/assign control or endpoint. | src/pages/AdminDashboard.tsx:290; backend/api/v1/admin.py:32 | Partial | Real data; role MANAGEMENT not implemented (view-only)
ADM-03 | Admin | Activity feed (events) | Admin | As an admin, I see a live feed of recent user events. | Activity Feed GET /api/admin/events (paginated learning_events LEFT JOIN profiles desc) shows event_type/user/timestamp/raw event_data. | src/pages/AdminDashboard.tsx:366; backend/api/v1/admin.py:78 | Functioning | Real, paginated
ADM-04 | Admin | Student content visibility | Admin | As an admin, I archive/publish courses and lectures. | Student Visibility tab toggles via POST /courses/{id}/toggle-visibility + /lectures/{id}/toggle-visibility (flip is_archived); toasts. | src/pages/AdminDashboard.tsx:99; backend/api/v1/admin.py:230 | Functioning | Real, flips is_archived
ADM-05 | Admin | Error logs (Sentry diagnostics) | Admin | As an admin, I view active error/issue reports. | Sentry Diagnostics GET /api/admin/errors; if SENTRY env unset returns configured:false + 3 hardcoded MOCK issues; UI shows 'Configuration Pending … simulated errors' banner; live fetch only when env set. | src/pages/AdminDashboard.tsx:525; backend/api/v1/admin.py:127 | Partial | MOCK/placeholder data unless Sentry env configured
ADM-06 | Admin | Analytics reset (purge) | Admin | As an admin, I wipe all analytics after a safety backup. | Reset & Restore multi-stage confirm; POST /reset-analytics requires confirmation=='RESET_ALL_DATA', calls reset_all_analytics RPC (snapshot then clear), returns backup_id; 5/min. | src/pages/AdminDashboard.tsx:130; backend/api/v1/admin.py:274 | Functioning | Real RPC (depends on stored proc)
ADM-07 | Admin | Backup list / restore / delete | Admin | As an admin, I view backup snapshots and restore or delete them. | GET /api/admin/backups lists snapshots; POST /backups/{id}/restore (confirmation=='RESTORE_DATA' + existence check + restore_analytics RPC); DELETE /backups/{id}. | src/pages/AdminDashboard.tsx:153; backend/api/v1/admin.py:292 | Functioning | Real (depends on analytics_backups + RPCs)
ADM-08 | Admin | Deployment / system diagnostics | Admin | As an admin, I see health/telemetry: DB status+connections, AI key, Sentry state, migration count, version, env. | Deployment Control GET /api/admin/deployment-info pings DB, counts pg_stat_activity, checks GEMINI_API_KEY+SENTRY_DSN, counts .sql migrations. | src/pages/AdminDashboard.tsx:777; backend/api/v1/admin.py:363 | Partial | Mostly real; app_version '0.1.0-alpha' + pool sizes hardcoded strings
FBK-01 | Feedback | Submit per-feature feedback | Any | As any signed-in user, I send free-text feedback about the screen I'm on. | Floating FeedbackWidget opens dialog (optional feature, required message ≤4000), attaches route, POSTs /api/feedback; verify_token + service-role insert into user_feedback with user_agent; 10/min; awards 'Voice Heard'. | src/components/FeedbackWidget.tsx:25; backend/api/v1/feedback.py:23 | Functioning | Real insert to user_feedback
FBK-02 | Feedback | Widget visibility scope | Any | As a user, the widget shouldn't appear where I'm not authenticated. | Hidden when no user or on /, /auth, /impressum*, /datenschutz*; rendered globally in ConsoleLayout. | src/components/FeedbackWidget.tsx:37; src/components/console/ConsoleLayout.tsx:89 | Functioning | Hidden on auth/landing
FBK-03 | Feedback | No feedback review surface | Admin | As an admin, I'd expect to review submitted feedback. | feedback.py only exposes POST; no GET and no admin tab reads user_feedback — write-only. | backend/api/v1/feedback.py:29 | Partial | Write-only; no review surface

## Dashboard
ascend-academy — Feature Audit Dashboard
Total user stories: 258 ¦ Branch: abdullah (post v1-restructure merge)
Feature Area | Total | Functioning | Partial | Broken | Unclear
Auth / Access / Settings | 39 | 32 | 4 | 1 | 2
PDF Upload & Parsing | 32 | 22 | 8 | 1 | 1
Courses / Enrollment / Library | 28 | 24 | 3 | 0 | 1
AI Content & Tutor | 21 | 16 | 4 | 0 | 1
Mind Map / Concept Graph | 8 | 8 | 0 | 0 | 0
Worksheets / Practice / Assignments | 24 | 23 | 1 | 0 | 0
Student Dashboard | 12 | 12 | 0 | 0 | 0
Nudges / Planner | 13 | 10 | 2 | 1 | 0
Onboarding / Academic | 10 | 9 | 1 | 0 | 0
Gamification | 16 | 14 | 2 | 0 | 0
Ranks | 5 | 5 | 0 | 0 | 0
Social / Leaderboard | 17 | 14 | 3 | 0 | 0
Analytics | 22 | 18 | 3 | 0 | 1
Admin | 8 | 5 | 3 | 0 | 0
Feedback | 3 | 2 | 1 | 0 | 0
TOTAL | 258 | 214 | 35 | 3 | 6
Phase tracking
P1 Code Status — derived from reading current code (this pass). DONE.
P2 Test Result — runtime test of each story; PASS / FAIL / BLOCKED. (pending)
P2 Errors/Notes — observed defects with repro. (pending)
P3 Fix Applied — logistical/UX fix landed. (pending)
P4 Retest Result — re-test after fix; PASS / FAIL. (pending)

## Test Log
Date | Phase | Item | Result | Detail
2026-06-24 | P2 | BUILD: Frontend typecheck | PASS | npx tsc --noEmit -p tsconfig.json → 0 errors. Frontend compiles clean after the v1-restructure merge.
2026-06-24 | P2 | BUILD: Backend import-check | FAIL→FIXED | Importing backend.main + all 17 v1 routers initially failed: 6 modules hit IndentationError at services/ai/tutor.py:124 (orphaned return False/return True from a removed refusal helper) → entire backend un-importable. Removed the dead lines → all 18 modules import OK.
2026-06-24 | P2 | TEST: Backend suite (pytest -m 'not db') | 617/677 PASS | After tutor.py fix + conftest patch repair: 617 passed, 12 failed, 9 errors. Failures/errors are predominantly test-infra staleness from the v1 restructure (monkeypatch targets moved API→service modules; stubs missing new kwargs) plus 4 diagnostics tests doing real network calls. No NEW product regressions identified yet.
2026-06-24 | P2 | FIX: conftest patch_supabase | FIXED | ai_content (v1) no longer exposes create_client (uses supabase_admin; AI create_client moved to tutor_service). Repointed conftest to patch database.create_client + ai_content.supabase_admin. Cleared the global 'ai_api has no attribute create_client' setup error.
2026-06-24 | P2 | TRIAGE: stale integration patches | OPEN | test_ai_endpoints patches ai_content.generate_summary (moved→tutor_service); test_check_duplicate patches upload.validate_upload (moved→upload_service); test_file_parse_service stub missing vision_model kwarg; test_auth_middleware mocks supabase_admin.auth.get_user (verify_token now uses httpx GET /user). To reconcile in Phase 3 as restructure test-debt.
2026-06-24 | P3 | FIX: backend test-debt reconciled | 638 PASS | Reconciled all 21 stale backend tests (repointed monkeypatch targets to service modules, updated stubs for vision_model kwarg + httpx verify_token, updated removed-refusal test, added fake_supabase created_at/updated_at, mocked diagnostics network). Backend suite: 638 passed / 0 failed / 0 errors. No product bugs masked.
2026-06-24 | P2 | TEST: Frontend suite (vitest) | 202/219→219/219 | Initial: 17 failed across 4 files (apiClient, analyticsService, professorOverview, LectureChat) — all from the /api→/api/v1 apiClient rewrite (stale MSW handler URLs) + removed tutor refusal text. Reconciled via dual /api+/api/v1 MSW handler registration + updated LectureChat mock. Frontend suite: 219 passed / 0 failed.
2026-06-24 | P2 | VERIFY: /api vs /api/v1 routing | NOT A BUG | Backend mounts only /api/v1/*. Suspected ~15 raw fetch(`/api/...`) call sites (NudgeBanner, useTTS, usePDFUpload, useLectureSubmit, FastUpload, conceptsService, worksheetsService) would 404. Ran uvicorn + curl: /api/* returns 307 → /api/v1/* via main.py:150 redirect_legacy_api; fetch follows 307 preserving method+body. Both conventions resolve. Minor: extra round-trip; watch cross-origin Authorization on redirect (same-origin via nginx is fine).
2026-06-24 | P2 | ENV: disk space | RESOLVED | Disk hit ~98% mid-run (one ENOSPC during vitest). Cleared vite/vitest/coverage caches (~4.7 GiB). Now ~72% used.
2026-06-24 | P3 | FIX: undeclared dep python-json-logger | FIXED | New untracked backend/core/logging_config.py (imported by main.py:17) needs pythonjsonlogger, but it was NOT in requirements.txt → fresh `pip install -r requirements.txt` deploy would fail to start the backend. It also went missing locally mid-session (disk cleanup). Reinstalled + added 'python-json-logger>=3.0' to backend/requirements.txt.
2026-06-24 | P3 | FIX: DomainError handler crash | FIXED | REAL BUG (surfaced once logging_config loaded): main.py:179 logged with extra={'msg': ...} — 'msg' is a reserved LogRecord attribute → logging raised KeyError, crashing the DomainError exception handler itself (every domain error would 500 in the handler). Renamed key to 'error_message'. test_api_v1_structure::test_domain_error_exception_handler now green.
2026-06-24 | P3 | FIX batch (logistical/UX) | 5 FIXED | SOC-13 leaderboard labels (This Week/All Time); PDF-02 parser_version default 2→5 (config + .env.example); AUTH-05 reset-password page+route; AI-20 unified ai_model allow-lists; NDG-12 planner card mounted (prior). All confirmed against the relevant Phase-1 finding before fixing.
2026-06-24 | P4 | RETEST: full suites + typecheck | ALL GREEN | After the Phase-3 batch: backend pytest 638 passed / 0 fail; frontend vitest 219 passed / 0 fail; tsc --noEmit 0 errors. (Runtime/browser confirmation of AUTH-05 recovery-link + NDG-12 render still needs a live authenticated stack.)
2026-06-24 | P2 | SCOPE: non-defect Partials | DOCUMENTED | Some Partial/Unclear items are config- or feature-scope, NOT code defects to 'fix': AI-02 (needs GEMINI_API_KEY), ADM-05 (Sentry mock unless SENTRY_* env), ADM-02 (admin role-management not built), ADM-08 (hardcoded app_version), FBK-03 (no feedback-review surface), NDG-08/13 (scheduler env flag / no budget UI). Recorded as known limitations rather than bug-fixed.
2026-06-24 | P3 | FIX batch 2 (logistical/UX) | 8 FIXED | AUTH-15 (deleted dead routeGuards+test); AUTH-34/38 (collapsed identical-branch JSX); ANL-12 (truthful feed label); PDF-29 (version-agnostic parser label); PDF-23 (configurable FAST_UPLOAD_MODEL); CRS-27 (removed Database-first sort bias); CRS-23 (no fabricated ratings — render only with real data); AI-08 (removed dead SSE branch from LectureChat).
2026-06-24 | P3 | DEFER: 3 items documented | DEFERRED | PDF-04 (Skip-AI no-op under v5 — needs product decision: honor on_demand vs hide toggle); PDF-05 (dead use_blueprint, dev-lab only); PDF-27 (Pipeline Test Lab v4-meta drift, professor-only dev inspector). Not silently changed; tracked in the workbook.
2026-06-24 | P4 | RETEST: full suites + typecheck (final batch) | ALL GREEN | After batch 2: backend pytest 638 passed; frontend vitest 209 passed (was 219 − 10 deleted dead-code tests); tsc --noEmit 0 errors. All landed Phase-3 fixes retested green.